## Summary
Count of Feature no | Column Labels
Row Labels | Available | Roadmap | Not Available | Grand Total
AISP | 29 | 8 | 5 | 42
CISP | 16 | 2 | 3 | 21
CMA |  | 14 | 8 | 22
Error handling | 10 |  | 1 | 11
Generic | 2 | 3 | 7 | 12
Logging and Monitoring | 25 | 2 | 3 | 30
PISP | 33 | 7 | 7 | 47
Sandbox | 1 | 1 | 3 | 5
SCA / Consent | 26 | 3 | 16 | 45
Security | 9 |  | 1 | 10
TPP Dev Onboarding | 27 |  | 2 | 29
TPP Onboarding | 22 | 19 | 3 | 44
Architecture | 6 |  |  | 6
Biz Analysis | 2 |  |  | 2
Platform | 4 |  |  | 4
Grand Total | 212 | 59 | 59 | 330

## Release Plan (MCR & MVP)
Delivery-Drop Features (Incremental) | 2017-06-30 | 2017-07-31 | 2017-08-31 | 2017-09-30 | 2017-10-31 | 2017-11-30 | 2017-12-31 | 2018-01-31 | 2018-02-28 | 2018-03-31 | 2018-04-30 | 2018-05-31 | 2018-06-30 | 2018-07-31
Release | 0.1 (MCR) | 0.2 (MCR) | 0.3 (MCR) | 0.4 (MCR) | 0.5 (MCR) | 1.1 (MVP) | 1.2 (MVP) | 1.3 (MVP) | 1.4 (MVP)
Functional | * AISP APIs - Single Account Information - Single Account Balance - Required Data Filtering for included APIs | * AISP APIs - Single Account Transaction - Required Data Filtering for included APIs * SCA & Consent (AISP) - One Brand - Channel Selection - Authentication - Consent UI - FraudNet Integration | * PISP APIs - Initiate Payment * PISP Other Functionality - Payment Authorization Checks - Payment Execution Checks - Exchange Rate Information - Payment Charges Information - Payment Terms and Conditions - Preventing duplicate requests - Support for internal retry - Transaction Monitoring For Fraud Prevention - Net Reveal Integration * CISP APIs - Funds Check - Required Data Filtering for included APIs * SCA & Consent (PISP & CISP) - MFA Inegration | * TPP Onboarding * Dev Onboarding * Sandbox environment (one brand) | * Complete MCR * SCA & Consent - All Four Brands (Minimal Branding themes) * CMA APIs - Account Beneficiary - Account Direct-Debits - Account Standing-Orders - Account Products - Required Data Filtering for included APIs | * AISP - Single Account Balance API - Data Masking - Single Account Transaction API - Data Masking * PISP - 1FA Consent Confirmation * CISP - 1FA Consent Confirmation * SCA & Consent - 1FA Authorization of consent | * AISP - Data enrichment - Customer account access validation * PISP - Payment Setup Checks - Beneficiary Validation - Payer Validation * TPP Onboarding - CISP Certification Validation | * PISP - Status Check API * SCA & Consent - Consent Management Self Service - View - Consent Management Self Service - Revoke - Consent Management Self Service - SSO login - Consent Management Self Service - Multibranding | * Multibranding - Detailed branding variations * TPP Onboarding Multibranding * Dev Onboarding Multibranding * Sandbox Multibranding
Utility APIs & Additional Features | 2017-07-31: * Customer Account List Service Integration * Foundation Service Mocking for dev and test; 2017-08-31: * Test Scenario Preparation * Test Data Preparation * Account Identifier Mapping * Consent List API * Consent Revoke API; 2017-09-30: * TPP Information API * TPP Block and Unblock API * Developer Block and Unblock API * Application Block and Unblock API * TPP Verification scheduler; 2017-10-31: * TPP Based throttling * Throttle API calls in sandbox * Access Token Revoke API * Refresh Token Revoke API
Platform | 2017-06-30: * Dev-Test Env Ready: 9-Jun; 2017-07-31: * SIT Env Ready: 1-Jul
Logging and Monitoring | 2017-07-31: * AWS VPC flow logging * Monitor JVM instances * Monitor AWS services; 2017-08-31: * Cloud watch alarms * Cloud watch actions * Cloud watch metric collection; 2017-09-30: * API Analytics-Number of API calls made by TPP * API Analytics-Number of API calls made by a PSU * Splunk Audit log; 2017-10-31: * TPP Activity Report * Support Reports; 2017-12-31: * Role based access control to indexes * Role based access control * Role based access to logged fields; 2018-01-31: * Integration with service now; 2018-02-28: * API Analytics - Custom analytics dashboards * Sandbox Analytics * Support GUI
Prerequisites | * AWS Account for Dev-Test: 5-Jun * Signoff on relevant Solution Blueprint and ICD: 1-Jun | * Signoff on relevant Solution Blueprint and ICD: 1-Jul * AWS Account for SIT: 23-Jun | * Signoff on relevant Solution Blueprint and ICD: 1-Aug | * Signoff on relevant Solution Blueprint and ICD: 1-Sep | * Signoff on relevant Solution Blueprint and ICD: 1-Oct | * Additional AWS Account for Dev-Test: 22-Sep * Signoff on relevant Solution Blueprint and ICD: 1-Nov | * Signoff on relevant Solution Blueprint and ICD: 1-Dec | * Signoff on relevant Solution Blueprint and ICD: 1-Jan | * Signoff on relevant Solution Blueprint and ICD: 1-Feb

## Estimation Summary
Sum of DCUT Effort Guesstimate (Mandays) | Major Release
| MCR | [6 empty] | Grand Total
Row Labels | Product Feature | Product Feature-New | Integration-Planned | Integration-New | Configuration-Planned | Custom Implementation-Planned | Custom Implementation-New
AISP | 300 | 50 | 0 |  | 20 | 176 | 60 | 606
CISP | 125 |  | 0 |  |  | 84 | 20 | 229
CMA |  | 350 |  | 120 |  |  |  | 470
Error handling | 95 |  |  |  | 0 | 56 |  | 151
Generic | 240 | 5 |  | 60 |  | 240 | 80 | 625
Logging and Monitoring | 220 | 20 |  |  | 0 | 42 | 10 | 292
PISP | 225 | 50 | 0 | 40 | 0 | 357 |  | 672
Sandbox | 80 | 10 |  |  |  | 14 | 30 | 134
SCA / Consent | 246 | 30 | 223 |  |  | 146 | 165 | 810
Security | 380 |  |  |  | 0 | 21 |  | 401
TPP Dev Onboarding | 335 |  | 0 |  |  | 21 |  | 356
TPP Onboarding | 210 | 165 | 0 |  |  | 21 |  | 396
Architecture | 420 | [6 empty] | 420
Biz Analysis | 320 | [6 empty] | 320
Platform | 440 | [6 empty] | 440
Grand Total | 3636 | 680 | 223 | 220 | 20 | 1178 | 365 | 6322
Sum of DCUT Effort Guesstimate (Mandays) | Major Release
| MVP | [5 empty] | Grand Total
Row Labels | Product Feature | Product Feature-New | Integration-Planned | Integration-New | Custom Implementation-Planned | Custom Implementation-New
AISP |  | 10 |  | 10 |  |  | 20
CISP |  | 10 |  | 10 |  |  | 20
Logging and Monitoring | 40 | 120 |  |  |  | 40 | 200
PISP |  | 30 | 40 | 40 | 20 |  | 130
Sandbox | [5 empty] | 90 | 90
SCA / Consent | 30 |  |  |  | 50 |  | 80
TPP Dev Onboarding | [5 empty] | 30 | 30
TPP Onboarding | [5 empty] | 30 | 30
Grand Total | 70 | 170 | 40 | 60 | 70 | 190 | 600

## All Features
Product Features Catalog
[16 empty] | For CAP to add (For Traceability) |  | BOI Notes |  |  | For BOI to add (For Traceability)
Feature no | Module | Feature | Feature Description | Availablity Status (Available, Roadmap, Not Available) | Classification (Product Feature, Product Feature-New, Integration-Planned, Integration-New, Custom Implementation-Planned, Custom Implementation-New) | Complexity | Dependency | BOI Comments | Capgemini Comments | Cost To (BOI/CAP) | Implementation By (Product/ProfServ) | Major Release | Drop | Estimation Assumptions / Comments | DCUT Effort Guesstimate (Mandays) | Traceability Document File Name | Traceability Section/Sub-Section Reference | BOI Priority (High, Medium, Low) | BOI Release | BOI Release Comment | BRD ID | BRD description | `
AISP-01a | AISP | Consent Application - User Confirmation - 1FA | An authorization step within consent management process, where customer is authorizing the details of the 'explicit consent' to TPP. This can be in the form of 1FA for customer to authorize the explicit consent while providing it. | Roadmap | Product Feature-New | Medium |  |  | 1FA authorization mechanism is not specified in regulation | CAP | Product | MVP | TBD | Need to request user to enter their password and validate it. Already planned integration with Foundation Service API would be utilized to validate the password | 10 |  |  | High | 2 - MVP | for MCR need tick box along with suitable text to confirm explicit consent. NEW FC entry required
AISP-01b | AISP | Consent Application - User Confirmation - 1FA - Integration | Integrate with 1FA for customer to authorize the consent while confirming it | Not Available | Integration-New | Low |  | Agreed MVP 20/06/2017 | * MVP * Step would be included as a aprt of the product. * Integration would be required. | BOI | ProfServ | MVP | TBD | Need to request user to enter their password and validate it. Already planned integration with Foundation Service API would be utilized to validate the password | 10 |  |  | High | 3 - Post MVP | for MCR need tick box along with suitable text to confirm explicit consent. NEW FC entry required
AISP-02 | AISP | Single Account Balance API | By using one IBAN for one account, one API call can return all different types of balances and account information for that account as per customer consent | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.1 |  | 40
AISP-03 | AISP | Single Account Transaction API | By giving one IBAN, a list of transactions for a specific date range can be retrieved for one account as per customer consent | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 80
AISP-04 | AISP | Single Account Balance API - Account identifier input | Ability to support other PSD2 in scope account formats to retrieve balances other than IBAN as unique identifiers – NSC & Account number and credit card numbers. | Roadmap | Product Feature-New |  |  |  | currently only IBAN input is supported | CAP | Product | MCR | 0.1 | Support for any alphanumeric string as an account identifier | 30
AISP-05 | AISP | Single Account Transaction API - Pagination | Pagination of data returned by API | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | Post MVP | TBD | Assuming pagination based on starting point and count of items to be returned | 30
AISP-06 | AISP | Single Account Transaction API - Account identifier input | Ability to support other PSD2 in scope account formats to retrieve transaction history other than IBAN as unique identifiers – NSC & Account number and credit card numbers. | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.2 | Support for any alphanumeric string as an account identifier | 20
AISP-07 | AISP | Routing Adaptor | Routing to different adapter to interface with different banking applications and services based on the static or dynamic logic. Routing can be implemented based on the account number or some other input parameter. | Available | Product Feature |  |  | This is currently not required as there is currently no integration with Omega program. | If it is very complicated the bank needs to let us know how to make a decision. Even in legacy systems may need to call different systems. This needs to be input from the bank to configure. This is an integration item. This can be used for both balance and Transaction enquiry services. | CAP | Product | POST Omega | TBD | 0 | 30
AISP-08 | AISP | Customer Account List Service | Service used to retrieve list of account for creating consent for a specific customer | Available | Product Feature |  |  |  | Product team reconfirm availability | CAP | Product | MCR | 0.2 |  | 20
AISP-09 | AISP | Customer Account list Service - Integration | Integration with Foundation Service(s) to retrieve list of accounts for creating consent for a specific customer | Available | Integration-Planned |  | Foundation Services |  |  | BOI | ProfServ | MCR | 0.2 |  | NA |  |  | High | 2018-01-01
AISP-11 | AISP | Proof of Possession | PoP is validated for JWT tokens, and CID/secret for TPP validation and replay prevention to ensure that the valid TPP is invoking an API. | Available | Product Feature |  |  | DB - may not be required if CMA design adopted | Can be switched off if not needed. Will verify the final CMA draft once available and decide to remove it if it is not needed | CAP | Product | MCR | 0.4 |  | 5
AISP-12 | AISP | Error code mapping | The bank wants to map all the error codes to one generic error code (400) to external world whilst they keep the details for internal technical/customer support | Available | Product Feature |  |  |  | Available and configurable | CAP | Product | MCR | 0.2 |  | 20
AISP-13 | AISP | JWT token | JWT token allows getting access token using refresh token. | Available | Product Feature |  |  | This feature needs to be reviewed in terms of CMA regulation |  | CAP | Product | MCR | 0.2 |  | 5
AISP-14 | AISP | Single Account Transaction API Output | Will get a JSON with standard ISO20022- CAMT.052 data. There will be a mapping effort for this | Available | Product Feature |  |  | As per CMA specification. |  | CAP | Product | MCR | 0.2 |  | 5
AISP-16 | AISP | Get TPP Information Service | This API platform internal function is designed to get TPP information so that it can be displayed when the customer is creating the consent TPP Legal Name, Registration ID and Type is displayed | Available | Product Feature |  |  | Should be TPP Name (not information) | TPP Legal Name, Registration ID and Type is displayed | CAP | Product | MCR | 0.4 |  | 40
AISP-17 | AISP | Restricting number of TPP requests per day | Restricting number of times TPP can make a call per day (4 times per day) when the customer is not present | Roadmap | Product Feature-New | Medium |  | BOI 16/06/2017 per CMA session Cap to estimate | * Agreed to be included as a part of product. But as the exact mechanism was not specified, it was not implemented. * Cannot be planned for MCR. Can be planned for Post MVP | CAP | Product | TBC | TBD | Assuming mechanism to identify "customer not present" is available | 40 |  |  | High | 4 - RTS | confirm throttling capability of product
AISP-18 | AISP | Multi-Account Transaction API - Integration | Integration with Foundation Service(s) to get transaction details for multiple accounts. The API will call for information per account and the API platform will aggregate the information. | Not Available | Integration-New | Medium | Foundation Services | Recommend 1 call to FS per account. Colin to clarify product capability OOTB with respect to the multi-account feature. Note that multi-account is optional under CMA. | * Post MVP * Design needs to be worked out | BOI | ProfServ | Post MVP | TBD | Integration with 3 different REST based Foundation Services. Assuming Mapping will be available before start. | 60 |  |  |  | 3 - Post MVP
AISP-19 | AISP | Multi-Account Transaction API - Pagination | Support for Pagination in the multi-account transaction API | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | Post MVP | TBD | Assuming pagination based on starting point and count of items to be returned | 60
AISP-20 | AISP | Single Account Transaction API - Integration | Integration with Foundation Service(s) to get transaction details for specific account for a given date range | Available | Integration-Planned |  | Foundation Services |  |  | BOI | ProfServ | MCR | 0.2 |  | NA
AISP-21 | AISP | Routing Adapter - Integration | Integration with bank's application to identify dynamic routing logic for a specific account identifier and account type | Available | Integration-Planned |  | Foundation Services |  |  | BOI | ProfServ | POST Omega | TBD | 0 | 60
AISP-22 | AISP | Multi-Account Balance API | Product will provide an API to retrieve balance and account information for multiple accounts | Available | Product Feature |  |  |  |  | CAP | Product | Post MVP | TBD | 0 | 40
AISP-23 | AISP | Multi-Account Balance API - Integration | Integration with Foundation Service(s) to get balance and account details for multiple accounts | Not Available | Integration-New | Medium | Foundation Services |  | * Post MVP * Design needs to be worked out | BOI | ProfServ | Post MVP | TBD | Integration with 3 different REST based Foundation Services. Assuming Mapping will be available before start. | 40 |  |  |  | 3 - Post MVP
AISP-24 | AISP | Multi-Account Balance API - Pagination | Support for Pagination in the multi-account balance API | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | Post MVP | TBD | Assuming pagination based on starting point and count of items to be returned | 40
AISP-26 | AISP | TPP Based throttling | Throttling TPP request based on CID | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 10
AISP-27 | AISP | Filtering | API performs filtering of the data received from foundation services and remove data elements based on the consent given by the customer | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.1 |  | 10
AISP-28 | AISP | Data Masking | API performs masking of the data received from foundation services and mask data elements based on custom data masking logic | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.1 |  | 10
AISP-29 | AISP | SCA and Consent (1 Brand) | SCA and Consent functionality for AISP would be same as common SCA functionality. For providing consent, user will be able to provide consent to share their account information, balance and transaction information with a TPP. User will be able to select one or more accounts and select duration for consent, specific attributes like balances, transactions, historic duration for transactions which they would like to share with the TPP. | Available | Product Feature |  |  | OK (expect this feature to be updated in light of CMA specifications) | Yes updated as per CMA now | CAP | Product | MCR | 0.2 |  | 20
AISP-30 | AISP | TPP Application Validation | Validating individual TPP Application upon invoking each API Validate CID/SECRET of the TPP Application | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
AISP-31 | AISP | Reference Token Validation | Structural, Signature and Expiry Validation of Passed reference Access Token | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
AISP-32 | AISP | Value Token Validation | Translate reference token into value token and validate structure, signature, expiry and revocation of value Access Token | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
AISP-33 | AISP | TPP Validation | Identify TPP from CID and validate the TPP and its revocation status against the bank's listing. The TPP validation is in addition to and separate from the TPP application validation. | Available | Product Feature |  |  | 1. Ask Santhosh to check AISP blueprint. 2. Revocation needs to be addressed in Week 4 | TPP Blocking process and API details have been shared | CAP | Product | MCR | 0.2 |  | 5
AISP-34 | AISP | Consent Validation | Ensure that the Consent is still valid and is not expired or revoked | Available | Product Feature |  |  |  | This is currently done during the Token validation | CAP | Product | MCR | 0.2 |  | 5
AISP-35 | AISP | SCA Validation | Verify SCA Validity and Expiry status of the SCA | Available | Product Feature |  |  |  | As per the updated PSD2 RTS, for certain activities, if SCA was performed within a certain duration, then it should be asked again. This feature is to check the validity of SCA as per these rules. For example, if SCA was done more than 90 days back, then it would be required to be done again before returning transaction history. | CAP | Product | RTS | TBD |  | 5
AISP-36 | AISP | Validate Scope (API Level) | Validate if the API call is as per the scope allowed. Scope is mapped to business functionality represented by an API or group of APIs. (For example, Balance or Transactions) | Available | Product Feature |  |  | Assume this is permissions. Update wording if so | Yes it is permission, but technical term in OAuth is "Scope" | CAP | Product | MCR | 0.2 |  | 5
AISP-37 | AISP | Validate Claims | Validate if the API call is for the claim defined in the token Claim is fine grained control under the business functionality. For example, what specific accounts could be accessed to get balance information | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
AISP-38 | AISP | Single Account Balance API - Integration | Integration with Foundation Service(s) to get balance and account information details | Available | Integration-Planned |  | Foundation Services |  |  | BOI | ProfServ | MCR | 0.1 |  | NA
AISP-39 | AISP | Single Account Balance API - Data Masking | Rules for data masking for the Account and Balance information | Available | Configuration-Planned |  |  | Shouldn't need masking here | Data masking is optional. Based on this comment, we assume that no masking is needed | BOI | ProfServ | MCR | 0.1 |  | 10
AISP-40 | AISP | Single Account Transaction API - Data Masking | Rules for data masking for the Account Transaction information | Available | Configuration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.2 |  | 10
AISP-41 | AISP | Multi-Account Transaction API | Product will provide an API to retrieve transaction information for multiple accounts | Available | Product Feature |  |  |  |  | CAP | Product | Post MVP | TBD | 0 | 40
AISP-44 | AISP | Identify customer present | The ability to identify whether the customer is present at the TPP during an API call | Roadmap | Product Feature-New | Low |  | BOI 16/06/2017 per CMA session Cap to estimate | * Agreed to be included as a part of product. | CAP | Product | RTS | TBD | Actual estimate can only be provided once a methodology is finalized during LLD phase. | 10 |  |  | High | 4 - RTS
AISP-46 | AISP | AISP | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 176
AISP-47 | AISP | NetReveal Integration Calls during Every AISP API Call | NetReveal needs to be invoked while making every API call. Details are still being worked out | Not Available | Custom Implementation-New |  |  |  |  | BOI | ProfServ | MCR | 0.4 | BOI needs to provide exact details of the integration needed | 60
Architecture-01 | Architecture | Overall Architecture | Design of the overall concept and architecture for the API Platform | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 80
Architecture-02 | Architecture | Product Selection | R&D on avaialble products and product shortlisting and selection | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 60
Architecture-03 | Architecture | API Gateway | E&D on API Gateway and Mule POC | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 40
Architecture-04 | Architecture | Security and Directory | R&D on Directry and Security products and Ping Directory POC | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 40
Architecture-05 | Architecture | API Design | Generic design and approach for API and Microservices | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 120
Architecture-06 | Architecture | Adapter Design | Generic design and approach for Adapter | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 80
BusinessAnalysis-01 | Biz Analysis | Directive Study | Sturdy of various directve and leagal standards | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 200
BusinessAnalysis-02 | Biz Analysis | Input Output Mapping | High level mapping of various data elements for API input and output | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 120
CISP-01 | CISP | SCA and Consent | SCA process for CISP is same as the common SCA process. User will be able to select one or more accounts for allowing the TPP to request Funds Check and select duration for consent Duration selection should not be available for BOI | Available | Product Feature |  |  | Single account only. Don't want duration.. | Multiple account selection is supported. The mechanism will be similar to that of AISP. (Restricting to one account would be additional efforts so can be planned for MVP if needed) We will plan to remove duration selection | CAP | Product | MCR | 0.3 |  | 40
CISP-02 | CISP | Consent Application - Accept Specific Account Identifier | Support accepting specific account identifier, alias or account number as an input for providing consent. In this case, user will then not have to select an account. | Roadmap | Product Feature-New | Medium |  |  |  | CAP | Product | Post MVP | TBD | An account number would be provided along with the request for consent | 30 |  |  |  | 3 - Post MVP
CISP-03 | CISP | Consent Application - Mapping Account Identifier - Integration | The ability for CISP to securely map account identifier / credit card with an account with Bank to allow them to perform funds check on credit cards. This is related to multiple accounts mapped using one Token | Available | Integration-Planned |  |  | TBC | Mapping design is shared | BOI | ProfServ | MCR | 0.3 |  | NA |  |  | High | 2018-01-01
CISP-04a | CISP | Consent Application - User Confirmation - 1FA | Perform 1FA for customer to authorize the consent while confirming it | Roadmap | Product Feature-New | Low |  |  | New requirement identified | CAP | Product | MVP | TBD | Need to request user to enter their password and validate it. Already planned integration with Foundation Service API would be utilized to validate the password | 10 |  |  | High | 3 - Post MVP | for MCR need tick box along with suitable text to confirm explicit consent. NEW FC entry required
CISP-04b | CISP | Consent Application - User Confirmation - 1FA - Integration | Integrate with 1FA for customer to authorize the consent while confirming it | Not Available | Integration-New | Low |  | Needs to be MVP | * MVP * Step would be included as a aprt of the product. * Integration would be required. | BOI | ProfServ | MVP | TBD | Need to request user to enter their password and validate it. Already planned integration with Foundation Service API would be utilized to validate the password | 10 |  |  | High | 3 - Post MVP | for MCR need tick box along with suitable text to confirm explicit consent. NEW FC entry required
CISP-05 | CISP | Secure API Access | Secure access to API utilizing OAuth 2.0 Access Token | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
CISP-06 | CISP | TPP Application Validation | Validating individual TPP Application upon invoking each API Validate CID/SECRET of the TPP Application | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
CISP-07 | CISP | TPP Based throttling | Throttling TPP request based on CID | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 5
CISP-08 | CISP | Reference Token Validation | Structural, Signature and Expiry Validation of Passed reference Access Token | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
CISP-09 | CISP | Value Token Validation | Translate reference token into value token and validate structure, signature, expiry and revocation of value Access Token | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
CISP-10 | CISP | TPP Validation | Identify TPP from CID and validate the TPP and its revocation status. The TPP validation is in addition to and separate from the TPP application validation | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
CISP-11 | CISP | Consent Validation | Ensure that the Consent is still valid and is not expired or revoked | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
CISP-12 | CISP | SCA Validation | Verify SCA Validity and Expiry status | Available | Product Feature |  |  | as PISP |  | CAP | Product | RTS | TBD |  | 5
CISP-13 | CISP | Validate API Access Scope | Validate if the API call is as per the OAuth scope allowed. OAuth Scope is mapped to business functionality represented by an API or group of APIs. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
CISP-14 | CISP | Validate API Access Claims | Validate if the API call is for the OAuth claim defined in the token OAuth Claim is fine grained control under the business functionality. For example, what specific accounts could be accessed for initiating payment | Available | Product Feature |  |  | as PISP |  | CAP | Product | MCR | 0.3 |  | 5
CISP-15 | CISP | Routing Adapter | Routing to different adapter to interface with different core banking applications and services based on the static or dynamic logic. Routing can be implemented based on the account number or some other input parameter. | Available | Product Feature |  |  |  |  | CAP | Product | POST Omega | TBD | 0 | 10
CISP-16 | CISP | Routing Adapter - Integration | Integration with bank's application to identify dynamic routing logic for a specific account identifier and account type | Available | Integration-Planned |  |  |  | Not planned in the first phase as will not be required till Omega is ready | BOI | ProfServ | POST Omega | TBD |  | NA
CISP-17 | CISP | Funds Check API | An API to accept funds check request from a TPP for confirming if the specified account of a specified user has enough funds as per the amount mentioned in the request. This API will be invoked with an account identifier and the amount for checking | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 40
CISP-18 | CISP | Funds Check API - Integration | Integration with Foundation Service(s) to perform funds check | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA
CISP-21 | CISP | CISP | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.3 | RFP Phase Planned Activity | 84
CISP-22 | CISP | NetReveal Integration Calls during Every CISP API Call | NetReveal needs to be invoked while making every API call. Details are still being worked out | Not Available | Custom Implementation-New |  |  |  |  | BOI | ProfServ | MCR | 0.4 | BOI needs to provide exact details of the integration needed | 20
CMA-01 | CMA | API definitions provided by CMA | There is a possibility that CMA will publish the API definitions for APIs that banks need to support. At the moment product supports ISO20022 format only and an assessment needs to be done when CMA finally release the specifications | Roadmap | Product Feature-New | Low |  |  |  | CAP | Product | MCR | 0.5 | Efforts for updating AISP Balance and Transaction APIs and PISP APIs. New CMA Specific AISP APIs are estimated separately | 40 |  |  | High | 1 - CMA
CMA-02 | CMA | Multiple endpoints per Brand | CMA mandates that separate API endpoints must be exposed for each brand along with rules around endpoint URLs | Roadmap | Product Feature-New | Low |  |  | There is a need to receive CMA spec to decide about complexity | CAP | Product | MCR | 0.5 | Same APIs would be exposed using a separate brand specific endpoint. | 20 |  |  | High | 1 - CMA
CMA-03 | CMA | Single Account Transaction API Output - JSON Format | Will get a JSON output as per CMA specification | Roadmap | Product Feature-New | Low |  |  |  | CAP | Product | MCR | 0.2 | Efforts included in CMA-1 | 20 |  |  | High | 1 - CMA
CMA-04 | CMA | CMA Account information API (CMA API: accounts) | An API to give account information as per CMA specification. CMA in contrast to PSD2 specifies a separate stand alone API for customer information. This is support CMA API "accounts" when caled with a specific account number | Roadmap | Product Feature-New | Medium |  |  |  | CAP | Product | MCR | 0.1 | This API will be sub-set of the one for balance. Assuming Mapping will be available before start. | 12 |  |  | High | 1 - CMA
CMA-05 | CMA | CMA Account information API (CMA API: accounts) - Integration | Integration with BOI service to get account information as required by CMA Account information API This is support CMA API "accounts" when caled with a specific account number | Not Available | Integration-New | Low |  | BOI 16/06/2017 - Please confirm which CMA API is being refrred to here as is not clear from description | * Functionality is part of the product (CMA-04). Integration would be required as a Professional Services work | BOI | ProfServ | MCR | 0.1 | Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. Need to identify the CMA remedy this is part of | 10 |  |  |  | 1 - CMA
CMA-06 | CMA | CMA Account Beneficiary API | APIs will retrieve the list of Direct Debits, Registered Beneficiaries, Standing orders as per CMA specification | Roadmap | Product Feature-New | Medium |  | To confirm this is not mandatory under CMA |  | CAP | Product | MCR | 0.5 |  | 12 |  |  | High | 1 - CMA | Challenge required
CMA-07 | CMA | CMA Account Beneficiary API - Integration | Integration with BOI service to get beneficiary information as required by CMA API | Not Available | Integration-New | Medium |  | To confirm this is not mandatory under CMA |  | BOI | ProfServ | MCR | 0.5 | Assuming integration with one professional service to implement the required functionality | 10 |  |  |  | 1 - CMA | Challenge required
CMA-08 | CMA | CMA-Phase 1- Services | The phase 1 items are hosted in the cloud hub but after the platform is completed, then the bank would like decommission cloud hub and host it within the platform. | Not Available | Custom Implementation-New | Medium |  |  | * Not critical for MCR and MVP * To be added to Product (post Jan 2018 update). * Migration would be custom efforts. Post migration, CMA specified future updates would be part of Product | BOI | ProfServ | Post MVP | TBD | 0 | 40 |  |  |  | 3 - Post MVP | needs to be covered during 6 week design.
CMA-09 | CMA | Create Consent with TPP | Ability to receive consent data from TPP on behalf of the customer. Staging Consent and updating consent flow as per CMA | Roadmap | Product Feature-New | Medium |  |  | Need documentation and ideally process flow | CAP | Product | MCR | 0.2 |  | 80 |  |  |  | 1 - CMA
CMA-10 | CMA | CMA-Consent management-permission | Specific permission codes have been identified for CMA - 13 specific permission codes have been identified for CMA. Permission codes are granular and the API would return data based on the permission codes sent in the API request | Roadmap | Product Feature-New | Medium |  |  |  | CAP | Product | MCR | 0.2 |  | 40 |  |  |  | 1 - CMA
CMA-11 | CMA | CMA- exposing data per cluster | Data filtering as per the data clusters | Roadmap | Product Feature-New | Medium | Foundation Services |  | There is a dependency on foundation layer spec | CAP | Product | MCR | 0.2 |  | 40 |  |  |  | 1 - CMA
CMA-12 | CMA | CMA- Unique AccountID | CMA has specified a unique accountID for every unique account. This accountID is something that the bank only knows and is different from the unique account number that is known both to the bank and the customer. | Roadmap | Product Feature-New | Low |  |  | This needs further discussion | CAP | Product | MCR | 0.3 |  | 10 |  |  |  | 1 - CMA
CMA-13 | CMA | Account Direct-Debits API | APIs will retrieve the list of direct-debit for an account | Roadmap | Product Feature-New | Low |  |  |  | CAP | Product | MCR | 0.5 |  | 12
CMA-14 | CMA | Account Direct-Debits API - Integration | Integration with BOI service to get direct-debit information as required by CMA API | Not Available | Integration-New | Low |  |  |  | BOI | ProfServ | MCR | 0.5 | Assuming integration with one professional service to implement the required functionality | 10
CMA-15 | CMA | Account Standing-Orders API | APIs will retrieve the list of standing-orders for an account | Roadmap | Product Feature-New | Low |  |  |  | CAP | Product | MCR | 0.5 |  | 12
CMA-16 | CMA | Account Standing-Orders API - Integration | Integration with BOI service to get standing-orders information as required by CMA API | Not Available | Integration-New | Low |  |  |  | BOI | ProfServ | MCR | 0.5 | Assuming integration with one professional service to implement the required functionality | 10
CMA-17 | CMA | Account Products API | APIs will retrieve product details for an account | Roadmap | Product Feature-New | Low |  |  |  | CAP | Product | MCR | 0.5 |  | 12
CMA-18 | CMA | Account Products API - Integration | Integration with BOI Service to get product details for an account | Not Available | Integration-New | Low |  |  |  | BOI | ProfServ | MCR | 0.5 | Assuming integration with one professional service to implement the required functionality | 10
CMA-21 | CMA | TPP Onboarding - TPP Registration - Validation with CMA Registry | CMA is expected to provide a TPP registry. Functionality is required to validate the TPP with this registry (Onboarding time validation) | Roadmap | Product Feature-New | High |  | Originally this was with ID "TPP Onboarding-09", changed to CMS |  | CAP | Product | MCR | 0.4 |  | 30 |  |  | High | 1 - MCR
CMA-22 | CMA | TPP Onboarding - TPP Registration - Validation with CMA Registry - Integration | Integrate with CMA registry to validate TPP (Onboarding time validation) | Not Available | Integration-New | High |  | Originally this was with ID "TPP Onboarding-10", changed to CMS | New integration point identified | BOI | ProfServ | MCR | 0.4 | Integration with registry service provided by CMA for verification of TPP | 60 |  |  | High | 1 - MCR
CMA-23 | CMA | CMA Multi-Account information API (CMA API: accounts) | An API to give account information as per CMA specification. CMA in contrast to PSD2 specifies a separate stand alone API for customer information. This is support CMA API "accounts" when caled without a specific account number | Roadmap | Product Feature-New | Medium |  |  |  | CAP | Product | MCR | 0.2 | This API will be sub-set of the one for balance. Assuming Mapping will be available before start. | 10 |  |  | High | 1 - CMA
CMA-24 | CMA | CMA Multi-Account information API (CMA API: accounts) - Integration | Integration with BOI service to get account information as required by CMA Account information API This is support CMA API "accounts" when caled without a specific account number | Not Available | Integration-New | Low |  |  |  | BOI | ProfServ | MCR | 0.2 | Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. Need to identify the CMA remedy this is part of | 10 |  |  |  | 1 - CMA
Error handling-01 | Error handling | Error code mapping | Ability to map business error codes to HTTP error code. The product has capability to map business and system errors encounter to HTTP status codes, for example timeout occurred while calling foundation service can be mapped to "501 service not available" HTTP status code | Available | Product feature |  |  |  | Error code mapping is configurable | CAP | Product | MCR | 0.4 |  | 10
Error handling-02 | Error handling | Error payload | Ability to send error details as part of error response payload | Available | Product feature |  |  |  | Error payload provides the ability to specify error code and error description | CAP | Product | MCR | 0.4 |  | 10
Error handling-03 | Error handling | Timeout handling | Ability to configure timeouts while calling foundation service | Available | Product feature |  |  |  | Timeouts are configurable | CAP | Product | MCR | 0.4 |  | 10
Error handling-04 | Error handling | Retry handling | Ability to configure retry option while calling foundation services. The system has capability to configure number of retries/retry delay as well as turn off the retry option for a specific foundation service call | Available | Product feature |  |  |  | Retries are configurable | CAP | Product | MCR | 0.4 |  | 20
Error handling-05 | Error handling | Error payload logging | Ability to log the error payload received from foundation service | Available | Product feature |  |  |  | All the errors received from foundation services are logged | CAP | Product | MCR | 0.4 |  | 5
Error handling-06 | Error handling | End to end transaction tracking | Ability to pass correlation id to map end to end transaction while calling foundation services so that errors can be debugged. For each request call to foundation service, the request contains an http header called "correlation ID ". Foundation services are expected to pass back the correlation id as part of response | Available | Product feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
Error handling-07 | Error handling | Error reporting | Ability to report errors encountered for each API based on given date range. The product provides ability to create custom dashboards for reporting all the API logs | Available | Product feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
Error handling-08 | Error handling | System failure handling | Ability to handle system failures such as zone and region failures. The product has capabilities to handle zone and region failures | Available | Product feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
Error handling-09 | Error handling | Alerting | Ability to generate alerts for critical failures or error threshold. The product currently support email notifications | Available | Product feature |  |  |  | Cloud watch alarms can be configured for error thresholds | CAP | Product | MCR | 0.4 |  | 10
Error handling-10 | Error handling | Error handling Configuration and Customization | Mapping and configuration for Error Handling | Available | Configuration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.4 |  | NA
Error handling-11 | Error handling | Error Mapping and Configuration | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 56
Generic-01 | Generic | PCI compliance | PCI compliancy of all modules within API platform | Roadmap | Product Feature-New | Low |  | Unless cards excluded from MCR |  | CAP | Product | MCR | NA | Product does not store any data which would need PCI Compliance. CAP need to provide details on what data is being stored and process and discuss if PCI compliance is required | 5 |  |  |  | High | 1 - MCR | Assuming Card data transmitted / stored
Generic-02 | Generic | Content Management (CMS) | Content Management systems to allow generic content change without separate change | Roadmap | Product Feature-New | High |  |  | * Post MVP * CAP to povide roadmap for CMS integratiton enhancement | CAP | Product | Post MVP | TBD | Implementing a CMS is not planned as of now and would need detailed discussion and scope/requirement analysis Config server is used to push the content to the U and provides functionality for build less UI content changes | 200 |  |  | Low | 3 - Post MVP
Generic-03 | Generic | Engagement Manager | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 220
Generic-06 | Generic | Test Scenario Preparation | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 15
Generic-07 | Generic | PSD2 Platform Specific Data Preparation | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 5
Generic-08 | Generic | AccountID Mapping | Functionality to MAP Account Number to a Account Identifier | Not Available | Custom Implementation-New |  |  |  |  | BOI | ProfServ | MCR | 0.3 | API Layer has to implement a mapping functionality to support the mapping of account numbers with IDs | 40
Generic-10 | Generic | AISP App | Sample AISP Application for testing | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 120
Generic-11 | Generic | Config Server | Config server design and implementation | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 120
Generic-12 | Generic | Google Tagging | Google tagging can be provided - BOI would need to provide link etc. To be added as new feature on backlog | Not Available | Custom Implementation-New |  |  |  |  | BOI | ProfServ | Post MVP | NA |  | 40
Generic-13 | Generic | TPP Block Verificatoin Schedule Run | Run a schedule task to verify the TPPs standing with Open Banking repository and block a TPP if required | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | Post MVP | NA |  | 40
Generic-14 | Generic | Architecture Update as per Reference Architecture | Update Product Architecture as per Bank's Mule Reference Architecture | Not Available | Custom Implementation-New |  |  |  |  | BOI | ProfServ | MCR | NA |  | 40
Logging and Monitoring-01 | Logging and Monitoring | Request payload logging | Ability to log input request payload in API logs. Logging of input payload can be turned on or off and it can be API specific | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-02 | Logging and Monitoring | Response payload logging | Ability to log API response payload in API logs. Logging of response payload can be turned on or off | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-03 | Logging and Monitoring | Data masking of logged payload | Ability to mask data before payload is logged in API logs. Data masking of payload can be turned on / off. | Available | Product Feature |  |  |  | If data masking is turned on then masked item cannot be search with the original value | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-04 | Logging and Monitoring | Data masking rules | Ability to specify data masking rules. Data masking rules can be configured in the form of regular expression | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-05 | Logging and Monitoring | Role based access control | Ability to control access for log data and reports based on user role and permissions. The access is controlled at a report level. (Individual fields of the report cannot be controlled as per user role) Minimal role customization would be planned in the MCR. Further customizations would be taken in MVP | Available | Product Feature |  |  | rewording required. Access to logs based on role. Confirm what logs (Splunk?) |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-06 | Logging and Monitoring | Log console authentication methods | Ability to integrate with LDAP / SAML. It is possible to manage user access to the logs by defining user accounts and permissions in an LDAP directory. SSO from any SAML based single sign on system is also supported | Available | Product Feature |  |  | needs clarification as what Feature is here | Updated as requested | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-08 | Logging and Monitoring | AWS VPC flow logging | Ability to capture AWS VPC flow logs (e.g. network logs, AWS Services, EPS Volumes) | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-09 | Logging and Monitoring | Encrypted log storage | Ability to encrypt the log storage. Log data storage encryption is provided by AWS EBS volume encryption. | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-10 | Logging and Monitoring | Centralized logging | Centralized logging and log aggregation is supported. A report can be created for data elements in different logs. | Available | Product Feature |  |  | needs clarification as what Feature is here | Updated as requested | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-11 | Logging and Monitoring | High availability of logging infrastructure | High availability of logging infrastructure components across multiple availability zones and regions using Splunk HA architecture | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-12 | Logging and Monitoring | Monitor JVM instances | Ability to monitor JVM resource utilization using Appdynamics Java agents | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-13 | Logging and Monitoring | Monitor AWS services | Ability to monitor AWS services using Cloud watch | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-14 | Logging and Monitoring | Cloud watch alarms | Ability to set alarms on AWS services. Cloud watch alarms can be configured for all the supported AWS services | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-15 | Logging and Monitoring | Cloud watch actions | Ability to trigger cloud watch actions / notifications such as Auto scaling and SNS notifications | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-16 | Logging and Monitoring | Cloud watch metric collection | Ability to capture cloud watch metrics, such as CPU/ memory utilization. Cloud watch metric can be defined using CLI or AWS console | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-17 | Generic | Foundation Service Mocking for development and test | Creating mock interface for foundation services for development of adaptors | Not Available | Integration-New |  |  |  |  | BOI | ProfServ | MCR | 0.2 |  | 60
Logging and Monitoring-17 | Logging and Monitoring | Integration- service now | Ability to integrate with the Service Now for alerts and monitoring on AWS resources | Not Available | Custom Implementation-New | High |  |  | * TBC Input required from SI re MCR/MVP. Ongoing work with Rishabh/Harm | BOI | ProfServ | MVP | TBD | Integration with Service Now to create ticket entry. Assuming Mapping will be available before start. | 40 |  |  | High | 2 - MVP
Logging and Monitoring-18 | Logging and Monitoring | API Analytics-Customized analytics dashboards | Ability to create custom analytics dashboards, using Splunk queriesis present. Out of the box dashboards would be used in the MCR. Additional custom dahsboards would be planned in the MVP release | Available | Product Feature |  |  | DB | No customs for first release only default | CAP | Product | MVP | TBD |  | 40
Logging and Monitoring-20 | Logging and Monitoring | API Analytics-Number of API calls made by TPP | Ability to view number of API calls made by a TPP based on date range, provided by Splunk | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 20
Logging and Monitoring-21 | Logging and Monitoring | API Analytics-Number of API calls made by a PSU | Ability to view number of API calls made by a PSU based on date range, provided by Splunk. The report will provide daily counts and monthly summation | Available | Product Feature |  |  | What level is this data at? | Data is provided for a PSU (Customer) and count is available for a date and month | CAP | Product | MCR | 0.5 |  | 20
Logging and Monitoring-22 | Logging and Monitoring | Sandbox Analytics | Developer & TPP onboarding and usage analytics (i.e. how many TPP registered, how many developers, applications are registered, and the application usage) | Roadmap | Product Feature-New | Medium |  |  | * TBC - Analysis to be done of analytics produced by Mulesoft across entire Bank. Rishabh to send JOC info on how this maight work. May be solutioned within BANK | BOI | ProfServ | MVP | TBD | Developer portal would need to be enhanced to provide reporting functionality reporting TPP and Dev analytics. Detailed requirements to be finalized and estimate might need to be revisited | 120 |  |  | High | 2 - MVP
Logging and Monitoring-23 | Logging and Monitoring | Monitor the monitor Capability | Ability to put monitoring components in various geographical regions for high availability and disaster recovery | Available | Product Feature |  |  | DB | This is a configurable feature | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-24 | Logging and Monitoring | Splunk Audit log | Ability to view report on which a user is viewing what reports and/or executing what search queries. Splunk maintains an audit log of all the access and queries executed by splunk on behalf of a logged in user | Available | Product Feature |  |  | A splunk user? | Yes this is for the splunk user. A user who is viewing the reports or executing queries | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-25 | Logging and Monitoring | Role based access control to indexes | Ability to control the access to index to a specific user role. This capability is provided by splunk at the index level. In case user access query across multiple index then splunk provides capabilities to execute query on only those indexes that user is allowed to search | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.4 |  | 10
Logging and Monitoring-26 | Logging and Monitoring | TPP Activity | Ability to view API calls made by a TPP for a user and what information they accessed for example when a TPP accessed balance API and what balance was returned etc | Roadmap | Product Feature-New | High |  | Potential to discuss alternative solution |  | CAP | Product | MCR | 0.5 | Data is being logged. Custom reports needs to be created | 20 |  |  | High | 1 - MCR | Am minimum capability is required for initial release.
Logging and Monitoring-27a | Logging and Monitoring | Support GUI | PARTIAL Out of the Box - Tool required to support Help Desk Level 1 and 2 support. How can bank staff get access to TPP API use information for customers | Not Available | Custom Implementation-New | Low |  | Potential to discuss alternative solution | Product Out of the Box dashboard could be used in MCR with minimal customizations | BOI | ProfServ | MCR | 0.5 | Splunk dashboards are already available. Further minor customizations can be performed for the required reports. Custom support portal is not considered in scope for MCR | 10 |  |  | High | 1 - MCR | Am minimum capability is required for initial release.
Logging and Monitoring-28 | Logging and Monitoring | API Analytics - Configuration | Configuration API Analytics logs as per the requirements | Available | Configuration-Planned |  |  | What is available OOB? | Details were shared in a session. Will plan to provide more details in an overview document | BOI | ProfServ | MCR | 0.4 |  | NA
Logging and Monitoring-29 | Logging and Monitoring | Cloud Watch - Configuration | Configuration Cloud Watch logs as per the requirements | Available | Configuration-Planned |  |  | What is available OOB? | Details were shared in a session. Will plan to provide more details in an overview document | BOI | ProfServ | MCR | 0.4 |  | NA
Logging and Monitoring-30 | Logging and Monitoring | Data masking - Configuration | Configuration of Data Masking rules. | Available | Configuration-Planned |  |  | What is available OOB? | Details were shared in a session. Will plan to provide more details in an overview document | BOI | ProfServ | MCR | 0.4 |  | NA
Logging and Monitoring-31 | Logging and Monitoring | Role based access control - Configuration | Finalizing the different roles and permissions which would be required by BOI for accessing various logs and reports | Available | Configuration-Planned |  |  | Not clear what feature is here. | Updated the description | BOI | ProfServ | MCR | 0.4 |  | NA
Logging and Monitoring-32 | Logging and Monitoring | Logging and Monitoring configuration | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 42
PISP-01 | PISP | SCA and Consent | SCA process for PISP is same as the common SCA process. Payment and payee information would be passed while requesting for consent and would be displayed to the customer/user. During consent process, user would be able to select a payment account for making the payment and provide their confirmation/authorization for the payment. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 40
PISP-02 | PISP | Consent Application - Accept Specific Account Identifier | Support accepting specific account identifier, customer account alias or account number as an input for providing consent. In this case, user will then not have to select an account. | Roadmap | Product Feature-New | Medium |  | BOI 16/06/2017 part of CMA mandated functionality. | * As per CMA, TPP can optionally, send the payer's account details. | CAP | Product | MCR | 0.3 | An account number would be provided along with the request for consent | 30 |  |  |  | 3 - Post MVP
PISP-03 | PISP | Consent Application - Payment Setup Checks | Performs checks and validations as per Bank's rules before displaying the consent page. In case of rule failure, the consent page will not be displayed. (for example due to blocked payee, country sanction, currency control) | Roadmap | Product Feature-New | Medium |  | Required for "viable" customer experience but not compliance | Validations itself assumed to be performed by Foundation Services and business rules to be provided by Bank | CAP | Product | MVP | TBD | 0 | 10 |  |  | High | 2 - MVP | Need to understand customer journey implications here. As a workaround , validation will now occur in 2 places (auth & execute)
PISP-04 | PISP | Consent Application - Payment Setup Checks - Integration | Integration with Foundation Service(s) to perform Pre-Validation checks | Not Available | Integration-new | Medium |  |  |  | BOI | ProfServ | MVP | TBD | Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. | 20 |  |  | High | 2 - MVP
PISP-05 | PISP | Consent Application - Payment authorization Checks | Performs payment authorization checks and validations as per Bank's rules once the account is selected. (for example funds checks) | Roadmap | Product Feature-New | Medium |  | For compliance assume one point in process where checks are performed |  | CAP | Product | MCR | 0.3 |  | 10 |  |  | High | 1 - MCR
PISP-06 | PISP | Consent Application - Payment authorization - Integration | Integration with Foundation Service(s) to perform payment authorization checks | Not Available | Integration-new | Medium |  | For compliance assume one point in process where checks are performed |  | BOI | ProfServ | MCR | 0.3 | Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. | 20 |  |  | High | 1 - MCR
PISP-07 | PISP | Consent Application - Payment Execution Checks | Performs payment execution checks and validations as per Bank's rules on submission of consent, before the authorization is complete. | Roadmap | Product Feature-New | Medium |  |  |  | CAP | Product | MCR | 0.3 |  | 10 |  |  | High | 1 - MCR
PISP-08 | PISP | Consent Application -Payment Execution Checks - Integration | Integration with Foundation Service(s) to perform Payment execution checks | Not Available | Integration-new | Medium |  |  |  | BOI | ProfServ | MCR | 0.3 | Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. | 20 |  |  | High | 1 - MCR
PISP-09 | PISP | Consent Application - Exchange Rate Information | Ability to display exchange rate information where the requested currency is different from account currency | Available | Product Feature |  |  | OK (MVP) |  | CAP | Product | MCR | 0.3 |  | 10
PISP-10 | PISP | Consent Application - Exchange Rate Information - Integration | Integrate with Foundation service to retrieve exchange rate information | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA
PISP-11 | PISP | Consent Application - Payment Charges Information | Display payment changes information and charge breakup details | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 10
PISP-12 | PISP | Consent Application - Payment Charges Information - Integration | Integrate with Foundation service to retrieve payment charges and charge breakup details | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA
PISP-13 | PISP | Consent Application - Terms and Conditions | Display "Terms of Use" information (if applicable) while taking user consent for a payment authorization | Available | Configuration-Planned |  |  | "Terms and Conditions and Framework contract information" s/b Terms of Use | Updated | BOI | ProfServ | MCR | 0.3 |  | NA
PISP-14 | PISP | Consent Application - Terms and Conditions - Details | Details and content for the Terms and Conditions and Framework contract information to be displayed during consent process | Available | Configuration-Planned |  |  | "Terms and Conditions and Framework contract information" s/b Terms of Use. IS Duplicate of 13? | This item is to get exact details from the bank about the terms and conditions which needs to be displayed/provided | BOI | ProfServ | MCR | 0.3 |  | NA |  |  | High | 2018-01-01
PISP-15a | PISP | Consent Application - User Confirmation - 1FA | Perform 1FA again for customer to authorize the payment consent while confirming it | Roadmap | Product Feature-New | Low |  | Core part of customer proposition | New requirement identified | CAP | Product | MVP | TBD | Need to request user to enter their password and validate it. Already planned integration with Foundation Service API would be utilized to validate the password | 10 |  |  | High | 2 - MVP | for MCR need tick box along with suitable text to confirm explicit consent. NEW FC entry required
PISP-15b | PISP | Consent Application - User Confirmation - 1FA - Integration | Integrate with 1FA for customer to authorize the consent while confirming it | Not Available | Integration-New | Low |  |  | New requirement identified | BOI | ProfServ | MVP | TBD | Need to request user to enter their password and validate it. Already planned integration with Foundation Service API would be utilized to validate the password | 10 |  |  | High | 3 - Post MVP | for MCR need tick box along with suitable text to confirm explicit consent. NEW FC entry required
PISP-16 | PISP | Secure API Access | Secure access to API utilizing OAuth 2.0 Access Token | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 10
PISP-17 | PISP | TPP Application Validation | Validating individual TPP Application upon invoking each API Validate CID/SECRET of the TPP Application | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
PISP-18 | PISP | TPP Based throttling | Throttling TPP request based on CID | Available | Product Feature |  |  | Is common? E.g. AISP 26? | Yes this is common functionality at TPP level | CAP | Product | MCR | 0.5 |  | 5
PISP-19 | PISP | Reference Token Validation | Structural, Signature and Expiry Validation of Passed reference Access Token | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
PISP-20 | PISP | Value Token Validation | Translate reference token into value token and validate structure, signature, expiry and revocation of value Access Token | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
PISP-21 | PISP | TPP Validation | Identify TPP from CID and validate the TPP and its revocation status. The TPP validation is in addition to and separate from the TPP application validation | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
PISP-22 | PISP | Consent Validation | Ensure that the Consent is still valid | Available | Product Feature |  |  | revoke n/a for PISP | Yes. Updated the description | CAP | Product | MCR | 0.3 |  | 5
PISP-23 | PISP | SCA Validation | Verify SCA Validity and Expiry status | Roadmap | Product Feature |  |  | expiry n/a for PISP | Expiry of SCA is still applicable as the API call should be invoked within a certain period of completion of SCA | CAP | Product | Post MVP | TBD |  | 5
PISP-24 | PISP | Validate Scope (API Level) | Validate if the API call is as per the scope allowed. Scope is mapped to business functionality represented by an API or group of APIs. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 5
PISP-25 | PISP | Validate Claims | Validate if the API call is for the claim defined in the token Claim is fine grained control under the business functionality. For example, what specific accounts could be accessed for initiating payment | Available | Product Feature |  |  | please clarify what fine grained control means here | Please refer to the example included in the description | CAP | Product | MCR | 0.3 |  | 5
PISP-26 | PISP | Routing Adaptor | Routing to different adapter to interface with different core banking applications and services based on the static or dynamic logic. Routing can be implemented based on the account number or some other input parameter. | Available | Product Feature |  |  |  |  | CAP | Product | POST Omega | TBD | 0 | 10
PISP-27 | PISP | Routing Adapter - Integration | Integration with bank's application to identify dynamic routing logic for a specific account identifier and account type | Available | Integration-Planned |  |  |  | Not planned in the first phase as will not be required till Omega is ready | BOI | ProfServ | POST Omega | TBD |  | NA
PISP-28 | PISP | Initiate Payment API | An API to accept a payment request from a TPP for initiation and execution of a payment. The API is to support credit transfer. Supports SEPA , SWIFT and BACS payments. The API accept subset of PAIN.001 message and can transform it to other supported formats for initiating Foundation Service | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 60
PISP-29 | PISP | Initiate Payment API - Integration | Integration with Foundation Service(s) to initiate payment | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA
PISP-30 | PISP | Initiate Payment - Preventing duplicate requests | Initiate Payment API support blocking of duplicate payments based on the payment reference ID sent by the TPP. If TPP sends a payment request within 24 hours with the same reference ID, it will be blocked from further processing | Available | Product Feature |  |  | Need error handling info here | Need to discuss what level of information is expected | CAP | Product | MCR | 0.3 |  | 5
PISP-31 | PISP | Initiate Payment - Support for internal retry | Initiate Payment API will retry invoking the initiate payment foundation services. By default three retries are supported. Number of retries and duration between retries is configurable | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 |  | 10
PISP-32 | PISP | Initiate Payment - Support for retry by TPP | Initiate Payment API support retry of same payment without performing the SCA and Consent within the life span of Access Token. If TPP do not receive a response or receive a technical error from platform, it can retry the same payment if the access token has not expired | Available | Product Feature |  |  | see updated text | removing "without performing the SCA and Consent" is not valid as the TPP retry does not need SCA again | CAP | Product | Post MVP | TBD | 0 | 10
PISP-33 | PISP | Initiate Payment - Beneficiary Validation | Validate beneficiary as per bank rules before a payment requested is processed for initiation and execution (Single step is used in MCR for all validations) | Available | Custom Implementation-Planned | Medium |  |  |  | BOI | ProfServ | MVP | TBD |  | 10 |  |  | High | 1 - Fraud | To be reviewed with CAP - Duplicates?
PISP-34 | PISP | Initiate Payment - Beneficiary Validation - Integration | Integration with Foundation Service(s) to perform Beneficiary Validations (Single step is used in MCR for all validations) | Available | Integration-Planned | Medium |  |  |  | BOI | ProfServ | MVP | TBD | Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. | 20 |  |  | High | 1 - Fraud | To be reviewed with CAP - Duplicates?
PISP-35 | PISP | Initiate Payment - Payer Validation | Validate payer as per bank rules and perform funds check before a payment requested is processed for initiation and execution (Single step is used in MCR for all validations) | Available | Custom Implementation-Planned | Medium |  |  |  | BOI | ProfServ | MVP | TBD |  | 10 |  |  | High | 1 - Fraud | To be reviewed with CAP - Duplicates?
PISP-36 | PISP | Initiate Payment - Payer Validation - Integration | Integration with Foundation Service(s) to perform Payer Validations. Pass the reference ID received during SCA from the fraud detection system (FraudNet) (Single step is used in MCR for all validations) | Available | Integration-Planned | Medium |  |  |  | BOI | ProfServ | MVP | TBD | Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. | 20 |  |  | High | 1 - Fraud-SCA
PISP-37 | PISP | Initiate Payment - Transaction Monitoring For Fraud Prevention | Invoke Transaction Monitoring system to performs checks for fraud prevention Pass the reference ID received during SCA from the fraud detection system (FraudNet) | Available | Custom Implementation-Planned | High |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA |  |  | High | 1 - Fraud-SCA
PISP-38 | PISP | Initiate Payment - Transaction Monitoring For Fraud Prevention - Integration | Integrate with Transaction Monitoring system (NetReveal) to performs checks for fraud prevention | Available | Integration-Planned | High |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA |  |  | High | 1 - Fraud-SCA
PISP-39 | PISP | Initiate Payment - Pre-Initiation Notification | Send notification to payer about the payment which is about to be initiated | Available | Product Feature |  |  |  | Not required by BOI | CAP | Product | Not required by BOI | NA | 0 | 10
PISP-40 | PISP | Initiate Payment - Pre-Initiation Notification - Integration | Integrate with Notification system to send pre-initiation notification to user/customer | Available | Integration-Planned |  |  |  | Not required by BOI | BOI | ProfServ | Not required by BOI | NA |  | NA
PISP-41 | PISP | Status Check API | An API to perform status check, based on a payment reference ID on a payment which was previously initiated by a TPP. API provides status information CAMT54 | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.3 | 0 | 40
PISP-42 | PISP | Status Check API - Integration | Integration with Foundation Service(s) to perform payment status check | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA
PISP-43 | PISP | PISP | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 310
PISP-44 | PISP | PISP - NetReveal Integration | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 47
PISP-45 | PISP | Consent Application - Display Available Funds | Display available funds to the customer during the consent process, after the customer has selected the account (the foundation layer will provide an 'available balance' response) | Roadmap | Product Feature-New | Low |  |  | Added as per suggestion by BOI | CAP | Product | MVP | TBD |  | 10
PISP-46 | PISP | Consent Application - Display Available Funds - Integration | Display available funds to the customer during the consent process, after the customer has selected the account (the foundation layer will provide an 'available balance' response) | Not Available | Integration-New | Low |  |  | Added as per suggestion by BOI | BOI | ProfServ | MVP | TBD |  | 10
Platform-01 | Platform | Platform Architecture | Design of the physical architecture and infrastructure | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 120
Platform-02 | Platform | Provisioning Script | Infrastructure Provisioning and configuration script | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 200
Platform-03 | Platform | Dev Ops | Design and Configuration of Dev Ops Process | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 60
Platform-04 | Platform | Security Configuration | Configuration of network and platform security elements | Available | Product Feature |  |  |  |  | CAP | Product | MCR | NA |  | 60
Sandbox-01 | Sandbox | Throttle API calls in sandbox | Ability to throttle the API calls in sandbox | Roadmap | Product Feature-New | Low |  | The functionality is unavailable but can be enabled. Throttling within the sandbox can be configured |  | CAP | Product | MCR | 0.4 | CID level throttling can be performed | 10 |  |  | High | 2018-01-01
Sandbox-03 | Sandbox | Sandbox Configuration | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  | With BOI/JOC for decision about Multibransing support | Default out of the box sandbox could be used for MCR without any customization and multi branding | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 14
Sandbox-04a | Sandbox | Sandbox Multibranding | PARTIAL - Support for 1 brands in Sandbox (This includes work for TPP and Dev Onboarding portals) | Not Available | Custom Implementation-New |  |  |  | One single brand based theme could be used for Sandbox for MCR | BOI | ProfServ | MCR | 0.4 |  | 30
Sandbox-04b | Sandbox | Sandbox Multibranding | Support for 3 additinal brands in Sandbox (This includes work for TPP and Dev Onboarding portals) | Not Available | Custom Implementation-New |  |  |  | 04a is part of MCR and 04b is part of MVP | BOI | ProfServ | MVP | TBD |  | 90
Sandbox-05 | Sandbox | Sandbox Design | Design and infrastructure for Sandbox environment | Available | Product Feature |  |  | Is this just browser based UI, what browser supported and is it a responsively designed site. | Yes it is a web UI. The UI layout would be responsive. Browser details added to description | CAP | Product | MCR | 0.4 |  | 80
SCA / Consent-01 | SCA / Consent | SCA and Consent- Mechanism | Web Browser or Mobile WebView are the mechanisms to support SCA and consent creation Internet Explorer v11+ Google Chrome v45.0+ Mozilla Firefox v38.0+ Safari v6.0+ Android browser (Android from 4.2+) | Available | Product Feature |  |  | Is this just browser based UI, what browser supported and is it a responsively designed site. | Yes it is a web UI. The UI layout would be responsive. Browser details added to description | CAP | Product | MCR | 0.2 |  | 20
SCA / Consent-02 | SCA / Consent | SCA and Consent- Connectivity | TLS (One way SSL) connection between server and user's web browser | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 10
SCA / Consent-03 | SCA / Consent | Initiating-Consent | Customer is able to invoke the consent creation process via a TPP | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 10
SCA / Consent-04 | SCA / Consent | Security- TPP Application validation | Validating individual TPP Application upon invoking SCA and consent process Validate CID/SECRET of the TPP Application | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-05 | SCA / Consent | Security- TPP Validation | Identify TPP from CID and validate the TPP and its revocation status. The TPP validation is in addition to and separate from the TPP application validation | Available | Product Feature |  |  | Similar to AISP (re revocation) |  | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-06 | SCA / Consent | Security- TPP Validation - Scope Validation | Validating TPP Action while invoking SCA and Consent creation process Validate if TPP is allowed to invoke the action for the purpose they are trying to invoke it for | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-07 | SCA / Consent | Channel Selection- Channel Selection Application | Option to select Channel before logging in (Landing Page) User can select appropriate Channel while logging in. Before they get to enter their credentials | Not Available | Custom Implementation-Planned |  |  | Core part of solution - need to select credential set |  | BOI | ProfServ | MCR | 0.2 |  | NA |  |  | High | 1 - MCR
SCA / Consent-08 | SCA / Consent | Channel Selection- Channel Selection Application Brand Specific URLs | Invoking the channel selection application using different URLs for different brands or same URLs with additional parameters | Not Available | Custom Implementation-New | Low |  | Branding part of minimum conceivable unless defer PO/AA |  | BOI | ProfServ | MCR | 0.5 | Need to discuss and finalize the approach | 5 |  |  | High | 1 - MCR
SCA / Consent-09 | SCA / Consent | Channel Selection- Channel Selection - Multi Branding - 1 additional brand | Theming for one additional brand | Not Available | Custom Implementation-New | Medium |  |  |  | BOI | ProfServ | MCR | 0.2 |  | 10 |  |  | High | 1 - MCR
SCA / Consent-10 | SCA / Consent | Channel Selection- Channel Selection - Multi Branding (3 Brands) | Theming for different brands | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.5 | RFP Phase Planned Activity | 28 |  |  | High | 1 - MCR
SCA / Consent-11 | SCA / Consent | SCA- Login | Login Application for User to login using their Bank credentials | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.2 |  | NA |  |  | High | 1 - MCR
SCA / Consent-12 | SCA / Consent | Branding- Login - Multi Branding (3 Brands) | Support theming for different brands of the Bank | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.5 | RFP Phase Planned Activity | 90 |  |  | High | 1 - MCR
SCA / Consent-13 | SCA / Consent | Branding- Login - Multi Branding - 1 additional brand | Theming for one additional brand | Not Available | Custom Implementation-New | Medium |  |  |  | BOI | ProfServ | MCR | 0.2 |  | 10 |  |  | High | 1 - MCR
SCA / Consent-14 | SCA / Consent | SCA- Login - Validate login credentials | Validating user's login credentials using the Bank's directory server or authentication service | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.2 | RFP Phase Planned Activity | NA |  |  | High | 1 - MCR
SCA / Consent-15 | SCA / Consent | SCA- Login - Validate login credentials - Integration | Integration with Bank's Service for validating user credentials | Available | Integration-Planned | Medium |  |  | Considering 5 simple integrations with 5 Foundation services APIs (Different brands will use same/similar channel) | BOI | ProfServ | MCR | 0.2 | RFP Phase Planned Activity | 195 |  |  | High | 1 - MCR
SCA / Consent-16 | SCA / Consent | SCA- Login - Multi Factor Authentication - Integration | Integration with Bank's Service for invoking 2FA/MFA | Available | Integration-Planned | Medium |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA |  |  | High | 1 - Fraud-SCA
SCA / Consent-17 | SCA / Consent | Fraud Detection- Login - Fraud Detection - Integration | Integration with Bank's Fraud detection systems | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.3 | RFP Phase Planned Activity | 28
SCA / Consent-18 | SCA / Consent | Fraud Detection- Login - Fraud Detection - Storing response | Storing fraud detection system response ID for use in later systems | Available | Product Feature |  |  | Where is this being stored? | It is stored locally in the system within the JWT Token | CAP | Product | MCR | 0.3 |  | 10
SCA / Consent-19 | SCA / Consent | SSO- Login - Create OpenID Connect Token | Create OpenID Connect token for SSO and customer identification | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.2 |  | 10
SCA / Consent-20 | SCA / Consent | Consent Application- Consent Application | User can review the action which TPP is requesting and select accounts (if not already populated) and provide their consent | Available | Product Feature |  |  | Configuration limited to selecting account due to CMA specification. (Will be updated as part of CMA?) | Description updated | CAP | Product | MCR | 0.2 |  | 56
SCA / Consent-21 | SCA / Consent | Branding- Consent Application - Multi Branding - 1 additional brand | Theming for one additional brand | Not Available | Custom Implementation-New | Medium |  |  |  | BOI | ProfServ | MCR | 0.2 |  | 10 |  |  | High | 1 - MCR
SCA / Consent-22 | SCA / Consent | Branding- Consent Application - Multi Branding (3 brands) | Support theming for different brands of the Bank | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.5 | RFP Phase Planned Activity | 28 |  |  | High | 1 - MCR
SCA / Consent-23 | SCA / Consent | SSO- Consent Application - SSO | Support OpenID Connect based SSO into Consent application | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.2 |  | 20
SCA / Consent-24 | SCA / Consent | Consent Application - Account Selection | Support user for selecting one ore more accounts (depending on type of action) for providing consent | Available | Product Feature |  |  | only applicable for AISP | No this would be applicable for PISP and CISP as well. | CAP | Product | MCR | 0.2 |  | 10
SCA / Consent-25 | SCA / Consent | Consent Application- Account Selection - Integration | Integration with Foundation Service to get list of accounts for a customer | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.2 |  | NA
SCA / Consent-27 | SCA / Consent | Consent Application- User Confirmation | Display consent summary and request user's confirmation | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-29 | SCA / Consent | Consent Application- Multi Factor Authentication - Integration | Integration with Bank's Service for invoking 2FA/MFA | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.3 |  | NA
SCA / Consent-30 | SCA / Consent | Consent Application- Create Consent | Create consent as per accounts and options selected by the user | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-31 | SCA / Consent | Consent Application- Auth Code | Generate OAuth 2.0 Authentication Code on completion of consent | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-32 | SCA / Consent | Logging & Error Handling- Error Handling | Provide appropriate HTTP error details for error and exception conditions | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-33 | SCA / Consent | Logging & Error Handling- Logging | Log trace and debug activities for auditing and debugging. | Available | Product Feature |  |  | DB |  | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-34 | SCA / Consent | Filtration | Provision of filters ( business rules) on attributes to retrieve consent information. Basic filters to remove a particular field is possible. | Available | Product Feature |  |  | What types of filters are referred to here? | Added details to the description | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-42 | SCA / Consent | TPP access blocked at core banking level | The ability for the bank to block access of a TPP on bank level via API and utility script | Roadmap | Product Feature-New | Medium |  | To be reviewed as part of detailed design. It needs to be considered whether this feature is needed. As a result, it might be decommissioned. The requirements needs to be discussed. | The ability to revoke or block access of a TPP is available via an API | CAP | Product | Post MVP | TBD |  | 20 |  |  | High | 3 - Post MVP | Subject to OOB way of blocking TPP access
SCA / Consent-43 | SCA / Consent | API for available consents | The API to return all the consents available for a customer for all the TPPs API returns the list of accounts provided in the consent. (List provide both Account IDs the actual numbers as per the current CMA specifications) | Available | Product Feature |  |  | What details does API return here? | Added details to the description | CAP | Product | MCR | 0.3 |  | 40
SCA / Consent-44 | SCA / Consent | Getting Access token | Access token is used while calling an APIs and is validated before the API access is granted to the TPP (or the Third Party Developer in the sandbox environment). It also provides details about scopes and claims which a caller can access. The life of access token is only 5 minutes as of now. Access token can be used across sessions. | Available | Product Feature |  |  | Amend "caller" to TPP | Updated the description as requested | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-45 | SCA / Consent | Refresh Token | This is the token that lasts for up to 90 days and once it's expired, SCA will be invoked. The TPP has to give the refresh token so that they get access token. Standard and configurable. Validation are customized . Token is linked to login. | Available | Product Feature |  |  | only applicable for AISP DB. | Applicable for AISP and CISP (but these are generic level feature descriptions) | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-47 | SCA / Consent | Alert System | In the login application if the system is down, there is appropriate messaging | Not Available | Custom Implementation-New |  |  |  |  | BOI | ProfServ | MCR | 0.2 | 0 | 5
SCA / Consent-48 | SCA / Consent | T&C Link | In the consent confirmation page there must be a placeholder to specify the consent T&C | Available | Product Feature |  |  | Not confirmation page & not consent T&Cs, just consent statement. | It was communicated earlier that certain, BOI specific terms and conditions needs to be added in the consent page. | CAP | Product | MCR | 0.2 |  | 5
SCA / Consent-49 | SCA / Consent | Proactive Alert System | Preemptive messaging to let the users know the system is going to be down | Not Available | Custom Implementation-New |  |  | BOI to confirm if this is a requirement | Expected to be basic product features Agreed MCR 9Development based on a custom input for the message) | BOI | ProfServ | MCR | 0.4 | 0 | 5
SCA / Consent-57 | SCA / Consent | FraudNet Integration - Additional | Additional steps and integration porints for FraudNet integration. FraudNet calls would be made multiple times during SCA and Consent Pages. Details are still being worked out | Not Available | Custom Implementation-New |  |  |  |  | BOI | ProfServ | MCR | 0.4 | BOI needs to provide exact details of the integration needed | 60
SCA / Consent-58 | SCA / Consent | NetReveal Integration - Additional | Additional steps and integration porints for NetReveal integration. NetReveal calls would be made multiple times during SCA and Consent Pages. Details are still being worked out | Not Available | Custom Implementation-New |  |  |  |  | BOI | ProfServ | MCR | 0.4 | BOI needs to provide exact details of the integration needed | 60
SCA / Consent-59 | SCA / Consent | Channel Selection - Responsive UI and support for different device screen sizes | Responsive UI screens along with through testing on multiple device screen sizes for Channel Selection Screen | Not Available | Custom Implementation-Planned | High |  |  |  | BOI | ProfServ | MVP | TBD |  | 20
SCA / Consent-60 | SCA / Consent | Login - Responsive UI and support for different device screen sizes | Responsive UI screens along with through testing on multiple device screen sizes for Login Screens | Not Available | Custom Implementation-Planned | High |  |  |  | BOI | ProfServ | MVP | TBD |  | 30
SCA / Consent-61 | SCA / Consent | Consent Application - Responsive UI and support for different device screen sizes | Responsive UI screens along with through testing on multiple device screen sizes for Consent Screens | Roadmap | Product Feature | High |  |  |  | CAP | Product | MVP | TBD |  | 30
SCA / Consent-62 | SCA / Consent | Consent Application - API for Revoke Consent | Internal API for Revoking consent. A utility script should also be provided to invoke this API | Roadmap | Product Feature-New | High |  |  |  | CAP | Product | MCR | 0.3 |  | 30
Security-01 | Security | DDoS prevention | Ability to detect and prevent DDoS attacks. The product currently use services provided by AWS (WAF & Cloud Front) for DDoS prevention. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 20
Security-03 | Security | Single tenant VPC | Ability to connect to corporate data center via dedicated VPC | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 10
Security-04 | Security | DNS routing policies | Ability to configure DNS routing policies. The product currently use AWS route 53 routing policies | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 10
Security-05 | Security | API gateway for API management | Ability to apply policies for APIs. The product currently use Mulesoft as an API gateway | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 10
Security-06 | Security | OAuth 2.0 protocol support | Ability to issue tokens and SCA via OAuth 2.0 protocol standards | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 240
Security-07 | Security | Proof of Possession (POP) | Ability to validate a TPP via POP | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 40
Security-08 | Security | Two way SSL | Ability to support Two Way SSL (MTLS) for API calls | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 10
Security-09 | Security | XML/JSON malicious content | Threat protection policy in API Gateway through JSON & XML | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.5 |  | 40
Security-10 | Security | Security related configuration and customization | Configuration Policies for Security requirements | Available | Configuration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.5 |  | NA
Security-11 | Security | Security Configuration | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 21
TPP Dev Onboarding-01 | TPP Dev Onboarding | TPP Dev - Registration | A Third Party Developer would be able to visit Developer Portal (custom) hosted in Sandbox to register them self to get access to sandbox API platform. They can use it to test their apps. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-03 | TPP Dev Onboarding | TPP Dev - Registration - Capturing Developer details for registration | Third Party Developer can provide following details while registering: * First Name * Last Name * Email ID (will also be used as login username) * Password * Organization Name (optional) * TPP Role/Type *Captcha TPP developer can provide all the details or minimal allowed ones. The platform allow the Developers to get started with minimal possible details and update additional details later. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 60
TPP Dev Onboarding-04 | TPP Dev Onboarding | TPP Dev - Registration - Unique values validation | Following values provided by TPP Developer during registration needs to be unique. * Email ID (used for username) If any of these values match an existed TPP in Sandbox, then an error is provided and registration process is suspended. (Developer can correct and resubmit) | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-05 | TPP Dev Onboarding | TPP Dev - Registration - Password Validation | Ensure password is as per configured strong password requirements. Default check is for * Length: minimum 8 characters * minimum 1 uppercase and 1 lowercase letter * minimum one digit * minimum one special character | Available | Product Feature |  |  |  | Configuration based on Code/Property | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-06 | TPP Dev Onboarding | TPP Dev - Registration - Confirmation | On successful submission of TPP Dev registration, provide a confirmation message to user | Available | Product Feature |  |  |  | Configuration based on email template | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-07 | TPP Dev Onboarding | TPP Dev - Registration - Confirmation - Record Creation | On successful submission of TPP Dev registration, store the developer data. With status as "Pending Activation" | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-08 | TPP Dev Onboarding | TPP Dev - Registration - Activation Link | On successful submission of TPP Dev registration, send an email with activation link to the provided email ID to confirm the email ID ownership. | Available | Product Feature |  |  |  | Configuration based on email template | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-09 | TPP Dev Onboarding | TPP Dev - Registration - Activation Received | Once the developer clicks on the link and system is able to record the activation, activate the developer. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-11 | TPP Dev Onboarding | TPP Dev Login | A third party developer can log on to Developer Portal (custom) using their username and password provided during registration process. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-12 | TPP Dev Onboarding | TPP Dev Login - Dashboard | Upon login, TPP Developer can view a Developer Dashboard which will provide following values: * First Name * Last Name * Email ID (will be username) * Contact Number * Country/Location * Organization | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Dev Onboarding-13 | TPP Dev Onboarding | TPP Dev Login - Dashboard - Available Data | Developer dashboard will provide following test data and tokens for the developers to enable them to create their applications and invoke APIs * Access Tokens * * 4 Access Token with AISP Scope * * 4 Access Tokens with PISP Scope * * 4 Access Tokens with both AISP and PISP Scope * * 4 Access Tokens with no scope * List of 10 customers (with valid login credentials) (with MFA disabled) (which can be used for SCA) | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 60
TPP Dev Onboarding-14 | TPP Dev Onboarding | TPP Dev Login - Actions | Upon login, TPP can select any of the following actions to perform further operations * Edit Details * Change Password * Register Application * Request Prod Access for an Application (User Instructions) | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-16 | TPP Dev Onboarding | TPP Dev - Change Password | Developer can login and perform action to change existing password. Developer has to provide their existing password while creating a new one | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-17 | TPP Dev Onboarding | TPP Dev - Change Password - Password Validation | Old password is validated for matching New password is validated as per configured strong password requirements. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-18 | TPP Dev Onboarding | TPP Dev - Change Password - Notification | On successful completion of TPP Dev Change Password, an email is sent to developer email ID to indicate that password has been updated. (password information is not shared in the email) | Available | Product Feature |  |  |  | Configuration based on email template | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-19 | TPP Dev Onboarding | TPP Dev - Forgot Password | Developer can select forgot password link to generate a new password. Developer can generate a new password by providing their username | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-20 | TPP Dev Onboarding | TPP Dev - Forgot Password - Password Generation Email | On submitting their username for forgot password, Developer will receive an email with a link to visit for generating a new password | Available | Product Feature |  |  |  | Configuration based on email template | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-21 | TPP Dev Onboarding | TPP Dev - Forgot Password - Password Generation | On clicking on the link in the email, developer will be able to provide a new password. Username of the developer will not be changed. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-22 | TPP Dev Onboarding | TPP Dev - Forgot Password - Password Validation | New password is validated as per configured strong password requirements. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Dev Onboarding-23 | TPP Dev Onboarding | TPP Dev- Forgot Password - Notification | On successful completion of new Password generation, an email is sent to the developer's email IDs to indicate that password has been updated. (password information is not shared in the email) | Available | Product Feature |  |  |  | Configuration based on email template | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-24 | TPP Dev Onboarding | TPP Dev - Edit Details | Developer can login and perform action to change certain details they had provided during the registration process. Developers can update following fields: * First Name * Last Name * Contact Number * Country/Location * Organization | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Dev Onboarding-25 | TPP Dev Onboarding | TPP Dev - Edit Details - Validations | While updating the data, all the validations which are applied during registration are applied for any changed data | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-30 | TPP Dev Onboarding | TPP Dev - Application Registration | Developer can login and perform action to register an application. Once application is successfully registered, developer will received CID/SECRET for the application which they can use to invoke APIs hosted in sandbox. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Dev Onboarding-31 | TPP Dev Onboarding | TPP Dev - Application Registration - Redirect to Mule with SSO | For registering an application, Mule application registration process would be used. For this purpose, developer will be redirect to Mule inbuilt developer portal. Developer will be able to log on to Mule developer portal using SSO. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-32 | TPP Dev Onboarding | TPP Dev - Application Registration - Mule Process | Mule Application Registration and API Assignment Flow is supported. This process involves: 1.Select API for Access 3.Select existing application or create new 3.Complete API to Application assignment and receive CID/SECRET. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Dev Onboarding-46 | TPP Dev Onboarding | TPP Dev - Support multi brand notification | Support for emails as per multiple brands of the bank. | Not Available | Custom Implementation-New | Medium |  |  | Single brand to be supported for MCR | BOI | ProfServ | MVP | TBD | Support for 4 different templates for 4 brands | 30 |  |  | High | 1 - MCR
TPP Dev Onboarding-47 | TPP Dev Onboarding | TPP Dev - Deactivate Developer API | API to deactivate Developer in Sandbox. If a Developer is deactivated, all its API access would be suspended. This API is not enabled for 3rd parties and can only be invoked by Bank. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 | 0 | 10
TPP Dev Onboarding-48 | TPP Dev Onboarding | TPP Dev - Email Server Integration | Integration with Bank's email server for sending notifications emails as required by developer portal | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.4 |  | NA |  |  | High | 2018-01-01
TPP Dev Onboarding-49 | TPP Dev Onboarding | TPP Dev On boarding Configuration | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 21
TPP Onboarding-01 | TPP Onboarding | TPP Registration (Non-OB Scenario) | A TPP would be able to visit the Developer Portal (custom) to register 'Organization + Its Applications' for access to API Platform of ASPSP | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-03 | TPP Onboarding | TPP Registration - Capturing TPP details for registration (Non-OB Scenario) | TPP can provide following details while registering: * Legal Name * Registered ID (as in certificate) * Qualified Digital Certificate (file) (for EBA Registration Verification) * * EBA Approved Type (Mandatory, pulled from certificate or manually selected) (as in certificate) * * * AISP, PISP, CISP * * * Custom (In case of special roles due to direct contracts with bank) * * Competent Registration Authority (as in certificate) * MTLS Digital Certificate (file) (for MTLS) (provide additional certificate or choose to use same as Digital Certificate) * Domain Names [take from certificate if available] * Primary Technical Contact ** First Name of PTC ** Last Name of PTC ** Title of PTC ** Phone number (optional) ** Email ID (used as username) ** Reconfirm Email ID * Login Credentials ** Username (same as Email ID) ** Password ** Reconfirm Password | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Onboarding-04 | TPP Onboarding | TPP Registration - Validation (Non-OB Scenario) | Following values provided by TPP during registration needs to be unique. * Username * Registration ID - Validate against Blacklist | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-05 | TPP Onboarding | TPP Registration - EBA Certification Validation (Non-OB Scenario) | The Digital Certificate provided to identify TPP as per EBA recommendations is validated for CA signature chain and structural consistency and expiry dates. OCSP (Online Certificate Status Protocol) is used to validate the revocation status of the certificate (for website certificates) Identify TPP Type from the certificate using extension filed "TPP_TYPE". Identify Registration Authority from the certificate using extension field "REGISTRATION_AUTHORITY" | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Onboarding-06 | TPP Onboarding | TPP Registration - MTLS Certification Validation (Non-OB Scenario) | The Digital Certificate provided for MTLS (if different from the EBA certificate) is validated for CA signature chain and structural consistency and expiry dates. OCSP (Online Certificate Status Protocol) is used to validate the revocation status of the certificate | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Onboarding-08 | TPP Onboarding | TPP Registration - Password Validation (Non-OB Scenario) | Ensure password is as per configured strong password requirements. Default check is for * Length: minimum 8 characters * minimum 1 uppercase and 1 lowercase letter * minimum one digit * minimum one special character | Available | Product Feature |  |  |  | Configuration based on code/property | CAP | Product | MCR | 0.4 |  | 20
TPP Onboarding-11 | TPP Onboarding | TPP Registration - Confirmation (Non-OB Scenario) | On successful completion of TPP registration, an email is sent to all contact persons email IDs to indicate registration confirmation. The ability to send this directly from the platform is supported as well as the ability to integrate with a bank's mail service if required. | Available | Product Feature |  |  |  | Configuration based upon email template | CAP | Product | MCR | 0.4 |  | 10
TPP Onboarding-12 | TPP Onboarding | TPP Login (Non-OB Scenario) | A TPP can log on to Developer Portal (custom) using the username and password provided during registration process | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-13 | TPP Onboarding | TPP Dashboard (Non-OB Scenario) | Upon login, TPP can view a TPP Dashboard which will provide following values: * Legal Name * EBA Registered ID * Digital Certificates (name info) * Domain Names * Contact Person * * First Name, Last Name * * Title * * Email ID * * Phone | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Onboarding-14 | TPP Onboarding | TPP Dashboard - Actions (Non-OB Scenario) | Upon login, TPP can select any of the following actions to perform further operations * Edit Details * Change Password * Manage Applications | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-15 | TPP Onboarding | TPP Login - MFA (Non-OB Scenario) | 2FA/MFA login process required for TPP Login | Not Available | Custom Implementation-New | High |  |  |  | BOI | ProfServ | Post MVP | TBD | 2FA product will be provided by BOI and would be interfaced using Foundation Services. Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. | 40 |  |  | High | 3 - Post MVP | Subject to IT Sec review
TPP Onboarding-16 | TPP Onboarding | TPP Change Password (Non-OB Scenario) | TPP can login and perform action to change existing password. TPP has to provide their existing password while creating a new one | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-17 | TPP Onboarding | TPP Change Password - Password Validation (Non-OB Scenario) | Old password is validated for matching New password is validated as per configured strong password requirements. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-18 | TPP Onboarding | TPP Change Password - Confirmation (Non-OB Scenario) | On successful completion of TPP Change Password, an email is sent to all contact persons email IDs to indicate that password has been updated. (password information is not shared in the email). The ability to send this directly from the platform is supported as well as the ability to integrate with a bank's mail service if required. | Available | Product Feature |  |  |  | Configuration based on email template | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-19 | TPP Onboarding | TPP Edit Details (Non-OB Scenario) | TPP can login and perform action to change certain details and certificates they had provided during the registration process. TPPs can update following fields: * ID Digital Certificate (file) * MTLS Digital Certificate (file) * Domain Name * Contact Persons | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Onboarding-20 | TPP Onboarding | TPP Edit Details - Validations (Non-OB Scenario) | While updating the data, all the validations which are applied during registration are applied for any changed data. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Onboarding-25 | TPP Onboarding | TPP Edit Details - Confirmation (Non-OB Scenario) | On successful completion of Edit Details, an email is sent to all contact persons email IDs to indicate update to the TPP data. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-29 | TPP Onboarding | Add Application - Invoke Bank Specific Approval process (Non-OB Scenario) | Initiate Bank Specific Approval Workflow to validate Certificates and other info provided by TPP. Default implementation - an email will be sent to a configurable email ID to perform the manual validation | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-30 | TPP Onboarding | Add Application - Invoke Bank Specific Approval process - Integration (Non-OB Scenario) | Integrate with bank specific approval system/mechanism to invoke specific approval process. | Available | Integration-Planned |  |  |  | This integration was not planned and estimated originally and would need to be estimated | BOI | ProfServ | MCR | 0.4 |  | NA |  |  | High | 2018-01-01
TPP Onboarding-32 | TPP Onboarding | TPP MTLS Certificate Provisioning | Once all approvals are complete, provision MTLS certificate into the TLS/SSL termination end point to enable MTLS communication. A notification would be sent to a pre-configured email and the process of taking the MTLS certificate and provisioning it would be a manual step. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Onboarding-33 | TPP Onboarding | TPP MTLS Certificate Provisioning - Integration | Integrate with bank specific notification mechanism / ticket system to invoke specific approval process. | Available | Integration-Planned |  |  |  | This integration was not planned and estimated originally and would need to be estimated | BOI | ProfServ | MCR | 0.4 |  | NA |  |  | Medium | 2018-01-01
TPP Onboarding-34 | TPP Onboarding | Block TPP API | API to Block a TPP . If a TPP is deactivated, all its API access would be suspended. It will not be able to log in and its applications will not work. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 | 0 | 40
TPP Onboarding-36 | TPP Onboarding | TPP Forgot Password (Non-OB Scenario) | TPP can select forgot password link to generate a new password. TPP can generate a new password by providing their username. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-37 | TPP Onboarding | TPP Forgot Password - Password Generation Email (Non-OB Scenario) | On submitting their username for forgot password, All TPP contact persons will receive an email with a link to visit for generating a new password. | Available | Product Feature |  |  |  | Configuration on email template | CAP | Product | MCR | 0.4 |  | 10
TPP Onboarding-38 | TPP Onboarding | TPP Forgot Password - Password Generation (Non-OB Scenario) | On clicking on the link in the email, TPP user will be able to provide a new password for the TPP. The username of the TPP will not be changed. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-39 | TPP Onboarding | TPP Forgot Password - Password Validation (Non-OB Scenario) | The new password is validated as per configured strong password requirements.. | Available | Product Feature |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-40 | TPP Onboarding | TPP Forgot Password - Confirmation (Non-OB Scenario) | On successful completion of new Password generation, an email is sent to all contact persons email IDs to indicate that password has been updated (password information is not shared in the email). The ability to send this directly from the platform, is supported as well as the ability to integrate with a bank's mail service if required. | Available | Product Feature |  |  |  | Configuration on email template | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-41 | TPP Onboarding | TPP - Support multi brand notification | Support for emails as per multiple brands of the bank. | Not Available | Custom Implementation-New | Medium |  |  | Single brand to be supported for MCR | BOI | ProfServ | MVP | TBD | Support for 4 different templates for 4 brands | 30 |  |  | High | 1 - MCR
TPP Onboarding-42 | TPP Onboarding | TPP - Email Server Integration | Integration with Bank's email server for sending notifications emails as required by developer portal | Available | Integration-Planned |  |  |  |  | BOI | ProfServ | MCR | 0.4 |  | NA
TPP Onboarding-43 | TPP Onboarding | TPP On boarding Configuration | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 21
TPP Onboarding-44 | TPP Onboarding | TPP Onboarding - TPP Registration - Validation with PSD2 Registry | PSd2 is expected to provide a TPP registry. Functionality is required to validate the TPP with this registry | Roadmap | Product Feature-New | High |  | Originally this was with ID "TPP Onboarding-09", changed to CMS |  | CAP | Product | Post MVP | TBD |  | 30 |  |  | High
TPP Onboarding-45 | TPP Onboarding | TPP Onboarding - TPP Registration - Validation with PSD2 Registry - Integration | Integrate with PSD2 registry to validate TPP | Roadmap | Product Feature-New | High |  | Originally this was with ID "TPP Onboarding-10", changed to CMS | New integration point identified | CAP | Product | Post MVP | TBD | Integration with registry service provided by PSD2 for verification of TPP | 60 |  |  | High
TPP Onboarding-46 | TPP Onboarding | TPP Login (OB Scenario) | A TPP can log on to Developer Portal (custom) using the username and password provided by OB. Login will be performed with OB and OIDC token will be received to login into the Developer Portal. TPP be allowed to log in if it is not in the Blacklist | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Onboarding-47 | TPP Onboarding | Add Application - Initiation | TPP should be able to login and request for addition of an application for getting Client ID and Secret | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-48 | TPP Onboarding | Add Application - Application Details - SSA (OB Scenario) | TPP should be able to upload an SSA (Software Statement Assertions) issued by OB for its validation for requesting CID and Secret for an application | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Onboarding-49 | TPP Onboarding | Add Application - Application Details - SSA Validation (OB Scenario) | Invoke OB request to validate the SSA (Software Statement Assertions) signature and TPP status. Validate following items: Validity of SSA Sign authority TLSMA via Network Kets If SSA is still Valid - from OB Redirect URL's TPP ID in SSA against party originating the request(network keys) TPP Role | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Onboarding-50 | TPP Onboarding | Add Application - Application Details - SSA Validation - Integration (OB Scenario) | Integration with OB Registry/system for SSA (Software Statement Assertions) and TPP Validation | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 20
TPP Onboarding-51 | TPP Onboarding | Add Application - Application Details - Get (Non-OB Scenario) | Gather Application Data 1. Financial Institution 2. Application Name 3. Redirect URL 4. Requested scope 5. Terms of use | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-52 | TPP Onboarding | Add Application - Application Details - Validation (Non-OB Scenario) | Use OCSP protocol & recheck the validity of the TPP certificate. Match TLS channel with "o" or "ou" in the certificate. Resolve the requested scopes against TPP scope. Scrub TPP name & Reg ID against bank provided blacklist. | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-53 | TPP Onboarding | Add Application - Generate CID/SECRET | Create application record and generate CID/SECRET with Mule for TPP Application | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
TPP Onboarding-54 | TPP Onboarding | Add Application - Display Application Details | Show application details on the "My Application" page with following details: 1. Application Name 2. Redirect URI 3. Grant types allowed 4. Scope 5 Client ID 6 Secret 7. Status | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-55 | TPP Onboarding | Remove Application - Initiation | TPP should be able to request for removal of an application | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-56 | TPP Onboarding | Remove Application - Delete Application Record | On receiving Remove Application request, Mark application record as inactive and remove its CID/Secret Inactive applications will not be visible in the "My Application" list | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 5
TPP Onboarding-57 | TPP Onboarding | TPP Blacklisting | API Platform support a configurable list which could be used to blacklist TPP. Bank can update this list (using support ticket mechanism) to not allow a TPP to register or login. | Roadmap | Product Feature-New |  |  |  |  | CAP | Product | MCR | 0.4 |  | 10
Note on T3: Colin Brick: 1 - MCR - minimum compliance release - may not operate at scale or deliver fully acceptable customer proposition 1 - CMA - required for CMA compliance 2 - MVP - minimum viable proposition - supports operation at scale and acceptable customer experience 3 - Post MVP - other requirements of the Bank 4 - RTS - not required until RTS date
Note on C76: Ramandeep Singh: Fixed the feature name and description to state multiple endpoint per brand (and not per TPP)
Note on C93: Ramandeep Singh: Split CMA and PSD2 related items into two different items to track CMA registry integration separately from PSD2 one
Note on C94: Ramandeep Singh: Split CMA and PSD2 related items into two different items to track CMA registry integration separately from PSD2 one
Note on C134: Ramandeep Singh: New task added to include additional efforts due to non-availability of Foundation Services during development. As Service Mocking need to be performed for integration
Note on C144: Ramandeep Singh: Feature is split into two for MCR and MVP
Note on C203: Ramandeep Singh: Feature is split into two for MCR and MVP
Note on C204: Ramandeep Singh: Feature is split into two for MCR and MVP

## Removed-Items
Feature no | Module | Feature | Feature Description | Availablity Status (Available, Roadmap, Not Available) | Classification (Product Feature, Product Feature-New, Integration-Planned, Integration-New, Custom Implementation-Planned, Custom Implementation-New) | Complexity | Dependency | BOI Comments | Capgemini Comments | Cost To (BOI/CAP) | Implementation By (Product/ProfServ) | Major Release | Drop | Estimation Assumptions / Comments | DCUT Effort Guesstimate (Mandays) | Traceability Document File Name | Traceability Section/Sub-Section Reference | BOI Priority (High, Medium, Low) | BOI Release | BOI Release Comment | BRD ID | BRD description
AISP-10 | AISP | Data enrichment | Enrich data based on certain business rules. For example the country code be converted to country name (IE to Ireland) | Not Available | Custom Implementation-New | Unknown |  | This feature needs reviewing during LLD and as a result it might be decommissioned |  | BOI | ProfServ | MVP | TBD | Need to get detailed requirements for data enrichment | Unknown |  |  | High | 2 - MVP | DB to confirm requirement
AISP-15 | AISP | Single Account Transaction API Output- Delta | Get Transaction API to return the delta of the transaction since the last time the TPP requested transactions for a specific customer for a specific account. This reflects the changes in transaction data. | Not Available | Custom Implementation-New | High |  |  |  | BOI | ProfServ | Post MVP | TBD | Significant design change and data caching would be required, unless the functionality is directly provided by the Foundation Services | 80 |  |  | High | 3 - Post MVP | OK
AISP-25 | AISP | Consent Application - Accept Specific Account Identifier | Support accepting specific account identifier, that has been entered via on the TPP side, customer account alias or account number as an input for providing consent. In this case, user will then not have to select an account. | Not Available | Custom Implementation-New | High |  |  |  | BOI | ProfServ | Post MVP | TBD | An account number would be provided along with the request for consent | 30 |  |  |  | 3 - Post MVP
AISP-42 | AISP | Customer account access validation | Validate the access status of the customer for the account during the API call to avoid information being shared which the customer should not be privy to | Not Available | Integration-New | Medium |  | Why is this required? Include more context in description. What happens if not present. |  | BOI | ProfServ | MVP | TBD | Validation would be performed by calling a Foundation Service | 5 |  |  | High | 1 - MCR | Assumption that Foundation Services will be used. LLD
AISP-43 | AISP | Customer account access validation - Integration | Integration with Foundation service to validate the customer account access | Not Available | Integration-New | Medium |  | Why is this required? Include more context in description. What happens if not present. |  | BOI | ProfServ | MVP | TBD | Integration with 2 different REST based Foundation Services. Assuming Mapping will be available before start. | 20 |  |  | High | 1 - MCR
AISP-45 | AISP | One Use Token | The ability for a customer to provide a TPP a one off consent which will only allow the TPP to request account information once. | Not Available | Custom Implementation-New | Medium |  | Bank to confirm with legal whether feature is part of PSD2 compliance |  | BOI | ProfServ | Post MVP | TBD | A token would be designed which will expire after single use. All other properties of the token will remain same | 30 |  |  | High | 3 - Post MVP
CISP-19 | CISP | Funds Check - Currency Conversion | Ability to perform currency conversion if the amount request for Funds Check is in a currency different from the currency of the account | Not Available | Custom Implementation-New | Low |  |  |  | BOI | ProfServ | Post MVP | TBD |  | 10 |  |  |  | 3 - Post MVP
CISP-20 | CISP | Funds Check - Currency Conversion - Integration | Integrate with foundation services to perform currency conversion for the funds check amount if it is in a currency which is different from account's currency. The same integration point will also perform the check for difference in the currencies to validate if conversion is required or not | Not Available | Integration-new | Low |  |  |  | BOI | ProfServ | Post MVP | TBD | Integration with 1 REST based Foundation Services. Assuming Mapping will be available before start. | 20 |  |  |  | 3 - Post MVP
CMA-19 | CMA | TPP Dev Onboarding - TPP Dev - Onboarding API | API based provisioning of 3rd party developers is required. Currently developers can be on boarded via UI. There is a need to enable API to perform developer onboarding with almost no manual steps. | Not Available | Custom Implementation-New | High |  | This feature could be CMA dependent | This was originally with ID "TPP Dev Onboarding-2", moved to CMA Section | BOI | ProfServ | Post MVP | TBD |  | 40 |  |  | High | 3 - Post MVP | Subject to CMA requirement (DB)]
CMA-20 | CMA | TPP Onboarding - TPP - Onboarding API | API based provisioning of the registration of 3rd parties is required. Currently TPPs can only be onboarded via UI. There is a need to enable API to perform onboarding with almost no manual steps | Roadmap | Product Feature-New | High |  | Bank (Dheepson) needs to get more understanding upon whether this is a CMA requirement. Our current understanding is that this is not a requirement from PSD2 or RTS but CMA might prescribe that provisioning needs to be provided by API | This was originally with ID "TPP Onboarding-02", Moved to CMA | CAP | Product | Post MVP | TBD | Detailed scope needs to be further defined. Process and rules for automatic validation needs to be defined | 60 |  |  | High | 3 - Post MVP | Subject to CMA requirement (DB)]
Generic-04 | Generic | SCA Mobile SDK - Android | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MVP | NA | RFP Phase Planned Activity | 29
Generic-05 | Generic | SCA Mobile SDK - iOS | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  |  | BOI | ProfServ | MVP | NA | RFP Phase Planned Activity | 22
Logging and Monitoring-07 | Logging and Monitoring | Role based access to logged fields | Ability to specify which user/role can access which payload logged field (for example user 1 can only see account number and user 2 can see both account number and account balance) | Not Available | Custom Implementation-New | Medium |  |  | *MVP. Field based access not required. Additional reports can be created for each individual report requirement. | BOI | ProfServ | MVP | TBD | This capability is not available with Splunk and would not be possible. | 10 |  | High | 2 - MVP
Logging and Monitoring-19 | Logging and Monitoring | API Analytics-service access to dashboard | Ability to expose custom dashboard / report as a service for internal users | Not Available | Custom Implementation-new | Medium |  | The feature needs to be confirmed during LLD. It needs to be discussed whether the feature is needed | Web service to expose dashboard data is not needed | [8 empty] | High | 2 - MVP | May remove this. TBC
Logging and Monitoring-27b | Logging and Monitoring | Support GUI | GUI and tools required to support Help Desk Level 1 and 2 support. How can bank staff get access to TPP API use information for customers Out of the box reports would be used in the MCR. Additnal functionality would be planned for MVP | Not Available | Custom Implementation-New | High |  | Potential to discuss alternative solution | 27a planned for MCR. 27b for MVP | BOI | ProfServ | MVP | TBD | Splunk dashboards are already available. Further minor customizations can be performed for the required reports. Custom support portal is not considered in scope for MCR | 120 |  | High | 1 - MCR | Am minimum capability is required for initial release.
Sandbox-02 | Sandbox | Automatic provision TPP into production | Currently a TPP has to come via Sandbox and then moved to production via manual steps. The bank require an ability to move a TPP based on certain rules automatically in to production | Not Available | Custom Implementation-New | High |  |  | Detailed business process required as well as requirements describing the rules to move a TPP into production | BOI | ProfServ | Post MVP | TBD | Detailed scope needs to be further defined. CMA Registry specs are required. Validation rules need to be defined Need to discuss if UI can be removed and only API based provisioning can be provided. | 80 |  |  | High | 3 - Post MVP | Confirm if mandatory under CMA (DB)
SCA / Consent-26 | SCA / Consent | Consent Application- Accept Specific Account Identifier | Support accepting specific account identifier for providing consent. In this case, user will then not have to select an account May not be needed for AISP | Not Available | Custom Implementation-New | Medium |  |  |  | BOI | ProfServ | MCR | 0.2 | Estimation included as a part of AISP, CISP and PISP | NA |  |  |  | 3 - Post MVP | Is Duplicate?
SCA / Consent-35 | SCA / Consent | Consent Management Self Service - View | Customers can login to consent application and view their consent (self service). | Not Available | Custom Implementation-New | High |  |  | BOI to provide requirements and details of the SSO methodology supported by the different channels | BOI | ProfServ | MVP | TBD | A UI application to support consent view and revocation by customer | 60 |  | High | 2 - MVP | Subject to this Information being available by other means
SCA / Consent-36 | SCA / Consent | Consent Management Self Service - Revoke | Customers can login to consent application and revoke their consent (self service). | Not Available | Custom Implementation-New | High |  |  |  | BOI | ProfServ | MVP | TBD | A UI application to support consent view and revocation by customer | 20 |  | High | 2 - MVP | Subject to this functionality being available to Bank. Need new FC item
SCA / Consent-37 | SCA / Consent | Consent Management Self Service - SSO login | SSO from other BOI application so that customers can login to consent application | Not Available | Custom Implementation-New | Medium |  |  |  | BOI | ProfServ | MVP | TBD | SSO mechanism for the self service consent management application | 20 |  | High | 2 - MVP
SCA / Consent-38 | SCA / Consent | Consent Management Self Service - Amend | Ability to add another account to the consent for example I want to add a my replaced credit card, new account number etc. | Not Available | Custom Implementation-New | Medium |  |  |  | BOI | ProfServ | Post MVP |  | Implementing Consent modification process. Not to be planned for Nov release | 80 |  |  | High | 3 - Post MVP | To be reviewed / deleted
SCA / Consent-39 | SCA / Consent | Consent Management TPP - Amend | Ability to add/remove another account to the consent via a TPP for example I want to add a my replaced credit card, new account number etc. | Not Available | Custom Implementation-New | Medium |  | To be reviewed as part of detailed design. The limitation of the product that the consent is at TPP level and customer level only needs to be considered. | The revoke API exists as part of the product, but an additional UI will be required to fully satisfy the regulatory requirement | BOI | ProfServ | Post MVP | TBD | Once the functionality is available for self service, expose it for TPP to amend the consent Not to be planned for Nov release | 40 |  |  | High | 3 - Post MVP
SCA / Consent-40 | SCA / Consent | Replay prevention | Prevent replay of the same SCA request. To be discussed in detailed design | Not Available | Custom Implementation-New | Unknown |  | Priority based on Capgemini comment - needs security review | SCA request cannot be replayed because of the login credential mechanism used, hence this feature should not be required. | BOI | ProfServ | Post MVP |  | Replay is not possible as of now. Need to discuss in LLD and explain the process | Unknown |  |  | High | 3 - Post MVP | To be reviewed / deleted
SCA / Consent-41 | SCA / Consent | Customer account access blocked at core banking level | The ability for the bank block access to certain account(s) which may be part of the consent that a customer has given to TPP | Not Available | Custom Implementation-New | High |  |  |  | BOI | ProfServ | Post MVP | TBD | PSD2 Product to provide an API which will enable bank to indicate an account as blocked. Might not be needed as the check is included as a new requirement | 40 |  |  | Medium | 3 - Post MVP
SCA / Consent-46 | SCA / Consent | Consent Application Hosting | Hosting consent application inside the BOI datacenter | Not Available | Custom Implementation-New | Low |  | To be confirmed |  | BOI | ProfServ | Post MVP |  | Custom application would be enabled for hosting within BOI data center. Hosting would be responsibility of BOI | 10 |  |  | High | 3 - Post MVP | Deleted Friday???
SCA / Consent-50 | SCA / Consent | Channel Selection Page (3 brands) | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  | Duplicate of "SCA / Consent-10" | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 28
SCA / Consent-51 | SCA / Consent | Login Page (3 brands) | RFP Phase Planned Activity | Not Available | Custom Implementation-Planned |  |  |  | Duplicate of "SCA / Consent-12" | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 90
SCA / Consent-52 | SCA / Consent | Login Integration (channel specific integration) | RFP Phase Planned Activity | Not Available | Custom Implementation-Planned |  |  |  | Duplicate of "SCA / Consent-15" | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 195
SCA / Consent-53 | SCA / Consent | FraudNet Integration | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  | Duplicate of "SCA / Consent-17" | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 28
SCA / Consent-54 | SCA / Consent | Consent Page UI Customization | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  | Duplicate of "SCA / Consent-20" | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 16
SCA / Consent-55 | SCA / Consent | Consent Page Branding (3 brands) | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-Planned |  |  |  | Duplicate of "SCA / Consent-22" | BOI | ProfServ | MCR | NA | RFP Phase Planned Activity | 28
SCA / Consent-56 | SCA / Consent | Consent Revoke Page & Functionality (3 Brands) | RFP Phase Planned Activity. Added to include estiamtion of planned activities as well | Not Available | Custom Implementation-New |  |  |  | Revoke UI to be planned in later phases | BOI | ProfServ | MVP | NA | RFP Phase Planned Activity | 68
TPP Dev Onboarding-10 | TPP Dev Onboarding | TPP Dev - Registration - Associate with TPP | Once the developer is activated, check if their email ID matches the domain specified by any already registered TPP. If it does, associate the developer with that TPP. Also update the inherited TPP Type for the developer to make it same as that of the associated TPP type. | Available | Product Feature |  |  |  | No longer required as per the updated design | [8 empty] | NA
TPP Dev Onboarding-15 | TPP Dev Onboarding | TPP Dev Login - MFA | 2FA/MFA login process required for TPP Dev Login | Not Available | Custom Implementation-New |  |  |  | No longer required as per the updated design | [8 empty] | 40
TPP Dev Onboarding-26 | TPP Dev Onboarding | TPP Dev - Edit Details - TPP Type Change Warning | If the TPP Type has changed, display a warning that this could cause existing applications to stop working (due to role/permission issues). | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-27 | TPP Dev Onboarding | TPP Dev - Auto Assign TPP Type | Developer can login and perform action to auto assign TPP type for them. For auto assigning a TPP Type, developer needs to be associated with a TPP. A TPP is associated with a developer using the domain name present in the email. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-28 | TPP Dev Onboarding | TPP Dev - Auto Assign TPP Type - Validate Developer Status | Verification that the developer account is active. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-29 | TPP Dev Onboarding | TPP Dev - Auto Assign TPP Type - Assignment | 1.Extract the domain name part of the email/username. 3.Search any existing organization with same domain name in its set. 3.Assign that TPP as developer’s organization and update developer record. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-33 | TPP Dev Onboarding | TPP Dev - Application Prod Access | TPP Developer can login and perform action to request production access for an application. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-34 | TPP Dev Onboarding | TPP Dev - Application Prod Access - TPP Association Validation | Validate if the developer is associated with a TPP. If not, then an error will be provided and the process suspended. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-35 | TPP Dev Onboarding | TPP Dev - Application Prod Access - TPP Production Access Validation | Validate if the TPP, with which the developer is associated with, is Enabled for Production Access. If not, then provide error and suspend the process. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-36 | TPP Dev Onboarding | TPP Dev - Application Prod Access - TPP Type update check | If the TPP's Organization Type has changed since last push to production, display Warning that the TPP organization's type in production is different from TPP type in Sandbox. Application access is restricted as per organization’s type and the application might not work properly in production. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-37 | TPP Dev Onboarding | TPP Dev - Application Prod Access - TPP Type match check | If TPP Type in production is different from the type used by developer in sandbox environment, Display Warning that the TPP organization type in production is different from the one used by the developer in sandbox and application might not work properly in production. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-38 | TPP Dev Onboarding | TPP Dev - Application Prod Access - Take testing confirmation | Request developer to confirm that they have performed thorough testing and verification for the application in the sandbox environment and are ready to move to production. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-39 | TPP Dev Onboarding | TPP Dev - Application Prod Access - TPP Approval | Send Approval Request Email to TPP’s Contact Persons (Any one of the contact person’s approval would be sufficient) (Share the details of the Application and the warning it might have raised). | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-40 | TPP Dev Onboarding | TPP Dev - Application Prod Access - TPP Approval Action | TPP Contact person (any one of the contact person) can click the link to approve the productiton access for an application. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-41 | TPP Dev Onboarding | TPP Dev - Application Prod Access - Invoke Bank Specific Approval process | Initiate Bank Specific Approval Workflow to validate application and provide production access (For product, put a placeholder for email link based approval on a pre-configured email ID). | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-42 | TPP Dev Onboarding | TPP Dev - Application Prod Access - Invoke Bank Specific Approval process - Integration | Integrate with bank specific approval system/mechanism to invoke specific approval process. | Available | Integration-Planned |  |  |  | No longer required as per the updated design | BOI | ProfServ | MCR |  |  | NA |  |  | High | 2018-01-01
TPP Dev Onboarding-43 | TPP Dev Onboarding | TPP Dev - Application Prod Access - Enablement | Once all approvals are complete, copy application configuration from Mule in Sandbox environment to Mule in Production environment and provide production CID/SECRET for the application. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-44 | TPP Dev Onboarding | TPP Dev - Application Prod Access - Enablement Notification for TPP | Send notification to all TPP contact person email IDs about Application Production Access enablement. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Dev Onboarding-45 | TPP Dev Onboarding | TPP Dev - Application Prod Access - Enablement Notification for Developer | Send application Production Access enablement notification to the Developer. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Onboarding-07 | TPP Onboarding | TPP Registration - CISP Certification Validation (Non-OB Scenario) | Need to support different type of certificates for specifically CISP (in addition to certificates for AISP and PISP). These certificates will be different from the one specified in the Directive/RTS. The product also needs to support registration of banks that are playing the role of TPP. | Not Available | Custom Implementation-New | High |  | Action for Darragh Peelo to verify whether the validation of the certification is prescribed within the directive. In case this is prescribed, please provide a reference to the section to the directive. | In reference to Article 29 of PSD2 regulation. Bank will provide more details about these certificates as the referenced article does not specifically specify this third type. | BOI | ProfServ | MVP | TBD | Detailed scope needs to be further defined. Process and rules for automatic validation needs to be defined | 20 |  |  | High | 1 - MCR
TPP Onboarding-21 | TPP Onboarding | TPP Edit Details - Already Prod Enabled - Warning | If the TPP has already enabled for Production Access, display a warning that the current changes will only be applicable in Sandbox till they explicitly push them to production (by requesting prod data update). | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Onboarding-22 | TPP Onboarding | TPP Edit Details - Already Prod Enabled - Validation while Removing Domain Name | If the TPP has already enabled for Production Access, and is removing/changing a domain name which was previously provided, do not allow this change as developer associations will break. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Onboarding-23 | TPP Onboarding | TPP Edit Details - Warning if TPP type changed | If TPP type is changed (through identification certificate or manually), display a warning that the TPP type has changed and might impact existing application (as they can all APIs as per the role and permission of the TPP). Also change the inherited type for all registered developers | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Onboarding-24 | TPP Onboarding | TPP Edit Details - Notification for Existing Person removed | If an existing contact person is removed, send them an email notification stating the change. . The ability to send this directly from the platform is supported as well as the ability to integrate with a bank's mail service if required. | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Onboarding-26 | TPP Onboarding | TPP Prod Access | TPP can login and perform action to request production access (or to update production data if they are already enabled in production). | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Onboarding-27 | TPP Onboarding | TPP Prod Access - Profile Validation | Ensure that the TPP has provided following details in their profile. Request them to update if any of the attributes are not present * Legal Name * EBA Registered ID * ID Digital Certificate (file) and TPP Type and Registration Authority details have been extracted from certificate * MTLS Digital Certificate (file). | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Onboarding-28 | TPP Onboarding | TPP Prod Access - Already Prod Enabled - Warning | If the TPP has already enabled for Production Access, Display Warning that any untested updates might break the existing working applications in PROD Ask TPP to ensure thorough testing in Sandbox | Available | Product Feature |  |  |  | No longer required as per the updated design | CAP | Product | MCR |  |  | NA
TPP Onboarding-31 | TPP Onboarding | TPP Prod Access - Enable TPP in Production | Once all approvals are complete, Activate given TPP App Access to system and issue the credential, certs for client App. | Available | Product Feature |  |  |  |  | CAP | Product | MCR |  |  | NA
TPP Onboarding-35 | TPP Onboarding | Custom TPP Role creation | Provide user interface to create new roles and permissions for custom TPPs. At present, new role can be configured in the directory server using standard LDAP tools. But this would be usable by Developers and Support teams. | Not Available | Custom Implementation-New | High |  |  |  | BOI | ProfServ | Post MVP | TBD | Admin UI and interface is required for managing the Roles | 80 |  |  | High | 3 - Post MVP
Note on T1: Colin Brick: 1 - MCR - minimum compliance release - may not operate at scale or deliver fully acceptable customer proposition 1 - CMA - required for CMA compliance 2 - MVP - minimum viable proposition - supports operation at scale and acceptable customer experience 3 - Post MVP - other requirements of the Bank 4 - RTS - not required until RTS date
Note on C16: Ramandeep Singh: Feature is split into two for MCR and MVP

## Feature Attribute
Users
MA | Maryam Aroni
JR | Jullien Rossel
Source
Data Type | Values
Driver | PSD2
CMA
BOI
Priority | High
Medium
Low
Complexity Rating | High
Medium
Low
If not available | If Regulatory | Priority | Is the feature available in the product ? (Available, Roadmap, Not Available)
Regulatory | CMA- Draft | High | Available
API Platform | CMA- Final | Low | Roadmap
| PSD2- Final | Medium | Not Available
PSD2- Draft
If API Platform | For bank to decide
Customer proposition | High
UI | Medium
Security | Low
Infrastructure
Standardization
Efficiency
Reporting & MI
Classification
BOI Input
Custom Implementation-new | Custom Implementation (not part of the out of box product features).
“New” indicate that this was not planned earlier during RFP and post RFP discussions
Custom Implementation-planned | Custom Implementation (not part of the out of box product features).
“Planned” indicate that this was already planned and estimated during RFP discussions
Integration - new | This is an integration item where we have to integrate with the BOI services
“New” indicate that this was not planned earlier during RFP and post RFP discussions
Integration - planned | This is an integration item where we have to integrate with the BOI services
“Planned” indicate that this was already planned and estimated during RFP discussions
Product Feature | Out of the box product features
Product Feature - new | New features identified.
These will be provided out of the box with no additional cost to BOI
Configuration - new | This is an configuration item where we have to discuss and identify the configuration needed.
“New” indicate that this was not planned earlier during RFP and post RFP discussions
Configuration - planned | This is an configuration item where we have to discuss and identify the configuration needed.
“Planned” indicate that this was already planned and estimated during RFP discussions