## Feedback List
Item # | # (per Matrix) | Doc Type | Version (date Received) | Doc Section | BoI Feedback Date | BoI Reviewer | BoI Feedback/Comment | CAP Response Date | CAP Responder | CAP Response | Status | Priority | RAG | Notes
INITIALS : SK - Santhosh Kumar, RD = Ravi Dhingra, EG = Emma Gilroy, DP = Darragh Peelo, AoH = Aisling O'Hagan, JC = J. Connor, CS = C. Saxena, CK = C.Kilbride, CR = C Rock, CB = C. Brick, , OK = Oonagh Koepern,
F001 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | CJ | Wireframes not included in document (approach to creating separate UX/Wireframe/Screens deliverable TBC) | 2017-06-13 | RAMAN | UI/UX is kept separate from the Blueprint. The API design can proceed in parallel with the UI/UX. UI Screens would be a separate document | Open | High | AMBER
F002 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | SK | Some API endpoints marked as ‘Pending Consent’ discussion. What is process to close this AISP document - should not all consent flows be contained in Consent Blueprint ? | 2017-06-13 | RAMAN | This would be covered in the SCA-Consent Blueprint. Updated document to reflect this | Open | High | AMBER
F003 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | SK | Document lacks a description of how 'pending consents' is handled by the product. | 2017-06-13 | RAMAN | We assume this is related to the "Consent Setup", this is covered in the SCA-Consent Blueprint | Open | High | AMBER
F004 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | SK | Document lack a description of how filtering transactions based on permission agreed in the Consent e.g. credit/debit, is handled(needs to be in Blueprint as opposed to ICD). | 2017-06-13 | RAMAN | Blueprint would be updated with the details. ETA 15-Jun | Open | High | AMBER
F005 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | SK | Document lacks a description of scenarios where requested txn date range fails to match available date range or consents etc. (needs to be in Blueprint as opposed to ICD). | 2017-06-13 | RAMAN | Blueprint would be updated with the details. ETA 15-Jun | Open | High | AMBER
F006 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | SK | Latest updates to CMA Spec must be incorporated into Blueprint -Account Request Status -Customer present vs not present -Technical information specified in the Latest document -Beneficiaries / Standing Orders / Direct Debits / Products endpoints inclusion(requires joint review w/c 12 June) | 2017-06-13 | RAMAN | This would be updated post discussion and understnading of CMA 1.0 RC. ETA 23-Jun | Open | High | AMBER
F007 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | DP | No reference to TPP validation rules in the Blueprint – what validations are being applied at each step of the sequence flow. | 2017-06-13 | RAMAN | Details are inclued in the cross functional diagram | Open | High | AMBER
F008 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | DP | Masking rule is not called out – what is the rule that is being applied – specific requirement shared with CAP (30th May from Santosh). Also, Can one or more rules can apply to a field? | 2017-06-13 | RAMAN | Blueprint would be updated with the details. ETA 15-Jun Following masking rule would be added for transaction entry: 1. Numeric (a continuous sequence of 8 numbers) 2. Name (a continuous sequence of 12 characters) | Open | High | AMBER
F009 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | DP | What happens if request for data is outside of the permission consented to (e.g. data cluster or time span) | 2017-06-13 | RAMAN | Forbidden error would be sent. Blueprint would be updated with the details. ETA 15-Jun | Open | High | AMBER
F010 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | DP | What are the error messages to be returned for each scenario | 2017-06-13 | RAMAN | This is being taken in a separate discussion related to Error Messages. Same list would be referred here | Open | High | AMBER
F011 | 3,4 | AISP ICD | 2017-06-05 |  | 2017-06-09 | DP | Applicable system column in excel spread sheet (Balance & transaction ICDs) not up-dated as per response provide (26th May) | 2017-06-13 | RAMAN | Updated to include "Payment Account" and "Credit Card" account categories Would be shared with the updated Blueprint. ETA 15-Jun | Open | High | AMBER
F012 | 3,4 | AISP ICD | 2017-06-05 |  | 2017-06-09 | DP | Single Account transaction ICD: Section 2 Overview states the following: This document aims to capture interface requirements for Account Transactions API that is invoked by a TPP (AISP) to retrieve account transactions of a single customer account identifier based on the consent authorization given to TPP (AISP) It should read: This document aims to capture interface requirements for Account Transactions API that is invoked by a TPP (AISP) to retrieve account transactions of a single customer account identifier based on the consent authorization provided by the customer | 2017-06-13 | RAMAN | Updated Would be shared with the updated Blueprint. ETA 15-Jun | Open | High | AMBER
F013 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | DP | These are the same diagrames that were presented in the initial playback & none of the feedback has been encorporated: 1.The sequence flows do not have headings on each of the pages – not clear what the activity of each flow is 2.Validation rules are not clear – suggested calling out what each of the validatiuons are that are being carried out – might not be in the sequence flow itself, though in the blueprint there should be a corrosponding description of each validation and how it ie executing it 3.We suggested not using the term ‘Get Data from Core Banking Systems’ as it suggested this was the CBS programme 4.One step is ‘Get Logic from Bank (if required)’ no description on what this is and what determines if it is required or not 5.All the blueprint documentation indicates balance & transaction information is based on single account, yet in the sequence flow there is the following reference ‘Aggregate Balance Information for all Accounts’ & ‘Aggregate transaction Information for all Accounts’ – this is confusing? | 2017-06-13 | RAMAN | Blueprint would be updated with the details. ETA 15-Jun | Open | High | AMBER
F014 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | Solution Blueprint: Is it necessary to add an section listing open design points, such as process/consent for Joint accounts, how to confirm if customer is present, any items awaiting CMA feedback, etc. | 2017-06-13 | RAMAN | Blueprint would be updated with the details. ETA 15-Jun | Open | High | AMBER
F015 | 1 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | Solution Blueprint: How is account id being generated, how is ID and account number being stored? | 2017-06-13 | RAMAN | This would be covered in a separate AccountID Mapping Approach document | Open | High | AMBER
F016 | 2,3,4 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | ICDs: updated data mapping provided to address number of TCB & TCD items this is not reflected in ICDs | 2017-06-13 | RAMAN | Please share the details and we will update the ICDs | Open | High | AMBER
F017 | 2,3,4 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | ICDs: Logging requirements – what is being logged in API product? | 2017-06-13 | RAMAN | Logging details are covered in a separate common document on Logging. Detailed deck has been shared | Open | High | AMBER
F018 | 2,3,4 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | ICDs: Error Handling – Error Payload/Code/Messages - needs to be included in Solution Blueprint for Business review | 2017-06-13 | RAMAN | This is being taken in a separate discussion related to Error Messages. Same list would be referred here | Open | High | AMBER
F019 | 2,3,4 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | ICDs – Balance & Transaction – Foundation Service input doesn’t include CC information and clarity if BIC/IBAN being passed | 2017-06-13 | RAMAN | We are not clear about this comment. Please rpovide mode information | Open | High | AMBER
F020 | 2,3,4 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | ICDs – API Transformation Requirements – applicable permissions listed but no detail on transformation requirements. | 2017-06-13 | RAMAN | Blueprint would be updated with the details. ETA 15-Jun | Open | High | AMBER
F021 | 2,3,4 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | ICD Transaction – Transaction start and end date: has approach been reviewed and agreed with Foundation services to alignment? | 2017-06-13 | RAMAN | Blueprint would be updated with the details. ETA 15-Jun | Open | High | AMBER
F022 | 2,3,4 | AISP Blueprint | 2017-06-05 |  | 2017-06-09 | LF | ICD Transaction – What is approach to filter based on Credit/Debit Transactions | 2017-06-13 | RAMAN | Blueprint would be updated with the details. ETA 15-Jun | Open | High | AMBER